Alameda Unified School District

Education Technology Plan

July 1, 2007 – June 30, 2010

Submitted to the Alameda Unified School Board

May 8th, 2007

Table of Contents

Acknowledgments 	3

District Summary and Plan Duration	8

(Criteria Item 1)

Stakeholders Involvement 	8

(Criteria Item 2)

Curriculum Driven Technology Goals	11

(Criteria Item 3)

Professional Development and Implementation	43

(Criteria Item 4)

Infrastructure, Hardware, Technical Support, 	53

and Software

(Criteria Item 5)

Funding and Budget 	63

(Criteria Item 6)

Monitoring and Evaluation 	68

(Criteria Item 7)

Effective Collaborative Strategies With Adult Literacy 	71

Providers to Maximize the Use of Technology Criterion 
(Criteria Item 8)

Effective, Research-Based Methods, Strategies, and Criteria	72

(Criteria Item 9)

Appendix:

A.  Computer specifications  ( May 2007 )

B.  Software specifications     ( May 2007 )

C.  Criteria for EETT Funded Education Technology Plans	77

E-Rate Addendum:

Acknowledgments

Board of Trustees

David Forbes

Janet Gibson

Tracy Lynn Jensen

Mike McMahon

Bill Schaff

### District Personnel

Curriculum and Data

Ardella Dailey, Superintendent

Debbie Wong, Assistant Superintendent—Educational Services

Barbara Lee, Director of K-8 Education and Curriculum

Donna Fletcher, Public Information Officer

Leni von Blanckensee, Assessment Coordinator

Sean McPhetridge, Director, Secondary Education / ROP

Technology Personnel

Jess Stephens, Director of Information and Technology Services

Magali Sourbs, Technology Services, Network Analyst

Sandy Keh, Technology Services, Technical Support

Terry Pinol, Technology Services, Application Support

#### Financial Personnel

Luz Cazares, Chief Financial Officer

Human Resources

Brandon Krueger, Chief Human Resource Officer

### AUSD Site Administrators

Mike Janvier, Principal, Alameda High School

Katie Lyons, Principal, Lum Elementary School

### AUSD Teachers

Dr. Phil Dauber, Alameda High School

Roxanne Clement, Bay Farm Elementary

Cindy Frankel, Lum Elementary School, Library and Media Center

Dianna Kenney, Teacher and Math Coach (EETT)

AUSD Parents / Students

Derrick Starks, Parent, Lum Elementary School

Ron Mooney, PTA Parent, Franklin Elementary School

### Government Agencies

CTAP Region 4 Tech Plan / Technology Coordinator – Melodee Munckton

### Community Group & Businesses

Mike Garneese, MultiMedia Computer Systems,

Steve Walker, ITEON Technologies. Alameda

Jane Chisaki, Alameda Free Library, City Of Alameda

District Profile

The Alameda Unified School District is located within the island City of Alameda, California.  The City of Alameda is located on the eastern side of the San Francisco Bay and is connected to Oakland by three bridges and one underground tube.  The following data offers a snapshot of our district during the 2006-07 school year from the Ed Data (http://www.ed-data.k12.ca.us/welcome.asp ) and Dataquest (http://data1.cde.ca.gov/dataquest/ ) web sites.

| Alameda Unified School District 2006-07 School Data |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Number of Schools | Enrollment | Full-Time Equivalent Teachers | Pupil-Teacher Ratio |
| Elementary | 10 | 4297 | 248.2 | 17.3 |
| Middle | 3 | 2267 | 105.2 | 21.5 |
| High School | 2 | 3103 | 139.3 | 22.3 |
| 6-12 (ACLC ) | 1 | 206 | 9.4 | 21.7 |
| Alternative | 1 | 84 | 3.9 | 15.6 |
| Continuation | 1 | 192 | 10.0 | 18.6 |
| Total | 18 | 10149 | 537 | 18.9 |

| Alameda Unified School District, Students by Ethnicity 2006-07 |  |  |
| --- | --- | --- |
|  | District Enrollment | Percent of Total |
| American Indian | 75 | 1.0% |
| Asian | 3153 | 31.0% |
| Pacific Islander | 153 | 2.0% |
| Filipino | 927 | 9.0% |
| Hispanic | 1203 | 12.0% |
| African American | 1330 | 13.0% |
| White | 3134 | 31.0% |
| Multiple/No Response | 186 | 2.0% |
| Total | 10163 | 100% |

| Alameda Unified School District, Student & Teacher Data 2006-07 |  |
| --- | --- |
| English Learners | 2147 21% |
| Fluent-English-Proficient Students | 1772 17.3% |
| Students Redesignated FEP | 160 7.4% |
| Graduates (prior year) | 671 |
| UC/CSU Elig Grads (prior year) | 211 |
| Dropouts (prior year, grade 9-12) | 64 |
| 1 Yr Drop Rate (prior year, grade 9-12) | 1.8 |
| 4 Yr Drop Rate (prior year, grade 9-12) | 7.1% |
| % Fully Credentialed Teachers | 95.7% |
| Pupil Teacher Ratio | 18.9% |
| Free or Reduced Price Meals | 3237 40.0 % |

Education Technology Plan

Overview

The Alameda Unified School District’s Educational Technology Plan describes how we  will integrate technology into the student learning process by implementing district wide curriculum, staff development and technology standards through five technology goals:

Curriculum – To improve student learning through technology rich instruction.

Computers – To provide all students with equal access to modern technology.

Connectivity – To provide all students with equal access to the Internet.

Competence – To train teachers/support staff on how to teach with technology and improve job performance.

Corporate – To deliver technology resources efficiently and equitably to all learners.

Strategic Plan

The Alameda Unified School District believes that all planning processes should support the underlying tenets of the districts values and objectives, namely quality education for our students.  This Educational Technology plan was developed with the following goals of the District’s Strategic Planning Process

ALAMEDA UNIFIED SCHOOL DISTRICT

STRATEGIC PLAN 2003-2008

The Alameda Unified School District embarked upon a 15-month Strategic Planning Process involving over 625 stakeholders representing students, parents, teachers and staff, site and district administrators, community leaders, and Board members. The resulting Strategic Plan provides a road map for achieving educational excellence that everyone in the district community comprehends and supports, and for aligning district resources behind the successful accomplishment of high-priority goals.

The District’s Strategic Plan contains a set of core values, which underscore the district’s commitment to diversity, and to the development of the whole person—emotional as well as intellectual intelligence. A new Mission Statement was defined affirming that AUSD is a team unified to ensure that every school creates a learning environment where every student succeeds.

All of the goals contained in the Strategic Plan are linked to a Strategic Focus, namely,

“every student will meet or exceed all AUSD and state standards as measured by district and state assessments.”  Working within agreed-upon Priority Goal Areas, a set of 12 Goals have been identified.

Curriculum/Instruction/Assessment

Goal#1: A clearly defined core curriculum, aligned with state standards, is being used consistently district-wide, and all educators are implementing effective instructional practices

Goal#2: A Staff Development Plan supports all educators in being more effective

Goal#3: Every student is being taught by fully credentialed, highly qualified teachers

Goal#4: A comprehensive assessment system is providing ongoing individual student data that enables teachers to be more effective in improving student performance

Strategic Intervention and Support

Goal#5: All at-risk students have equal access to effective intervention programs that help them get back on track academically

Goal#6: Every student graduates from high school

Goal#7: All limited-English-proficient students become proficient in English and reach high academic standards

Goal#8: Every Title I school has a high-quality Early Childhood Education Program

Student Involvement and Engagement

Goal#9: All students have the opportunity to be actively involved in decisions regarding their educational experiences

Safe Schools

Goal#10: All students are being educated in learning environments that are safe and conducive to learning

Vocational/Career/Adult Education

Goal#11: All students are prepared to succeed in college and/or their career choice because they have been exposed to a range of options that include career and technical education experiences

Communications and Community Engagement

Goal#12: An effective communication system promotes information exchange, and engages our diverse population in support of every student being successful

Educational Technology Plan

This updated AUSD Educational Technology Plan is a component of the AUSD Mission and Goals.  It is intended to serve as both a guide for technology related decision making and an instrument to monitor and evaluate progress toward identified goals and objectives. An updated assessment of district technology status, needs, and resources has been completed for each section of our revised technology plan and has guided the development of our new technology goals, objectives and implementation activities. Our goals and objectives were established to meet the identified needs of  integrating technology to improve student learning; providing equitable technology access and support; providing secure, timely information flow between home, school, and community; and providing coordinated, ongoing high quality educational technology professional development.

1a. Plan Duration

The Alameda Unified School District Education Technology Plan covers three years, from July 1, 2007 through June 30, 2010.  It will serve as the primary tool to guide the District’s acquisition, sustainability, and integration of technology to support the district’s curricular goals. This plan will be monitored by AUSD curriculum, data, and technology administrators, school administrators and school media specialists during quarterly education support meetings and reviewed and revised annually after the state releases achievement data for district school sites. Any modifications required through such review will be communicated to both the district Superintendent and school board. The district Director of Technology Services will then work with the Superintendent and Assistant Superintendent of Education Services to implement any required revisions directly with site-based administrators.

2a. Stakeholders

An Executive Writing Team was organized to review and revise the previous Technology Use Plan for the Alameda Unified School District. The previous plan expires at the end of the 2006-2007 School Year. The Executive Writing Team consisted of teachers, administrators from a variety of departments, including Curriculum, Educational Services, Technology, Fiscal and Human Resources; parents; the public library director; and members of the local business community.  This team met on a regular basis from early December 2006 through April 2007.  At various times throughout the process the plan was taken to Executive Cabinet, Administrative Staff, and the Educational Services Staff for additional input.

As stakeholders reviewed the technology plans outcome and process data, the following key questions were addressed:

- Is the district and schools’ visions for student success aligned to today's knowledge-based, Digital Age? Are administrators committed to the vision?

- Is student academic achievement improving where technology is being used effectively?

- Are students demonstrating proficiency in technological literacy?

- Are educators proficient in implementing, assessing and supporting a variety of effective practices for teaching and learning?

- Do students and school staff have robust access to technology - anytime, anywhere - to support effective designs for teaching and learning?

- Is the digital divide being addressed through resources and strategies that ensure that all students are engaging in an educational program aligned to the district’s vision of technology integration?

The Executive Writing Team met on an ongoing basis for several months during the development of this plan.  Grade Level Focus Teams, Community Stakeholders and the District Specialty User groups participated in the formative evaluation of the plan.  These groups reviewed the working plan and offered feedback. The Executive Writing Team used the feedback to revise the plan as necessary.

The District held two separate meetings for the purpose of reviewing and gathering input on the plan. These meetings were held at different locations within the district to encourage participation and facilitate the input process.  Additionally, drafts of the plan were posted to the District’s web site for community review and comment.

The AUSD Technology Planning Team consists of four groups:

The Executive Writing Team

- Barbara Lee, Director of K-8 Education and Curriculum

- Donna Fletcher, Public Information Officer

- Leni vonBlanckensee, Assessment Coordinator

- Sean McPhetridge, Director, Secondary Education / ROP

- Dr. Phil Dauber, Alameda High, Teacher and Department Chair

- Roxanne Clement, Bay Farm Elementary, Library Media Specialist

- Diana Kenney, Teacher and Math Coach  ( EETT )

The Grade Level Focus Teams

Elementary School

- Katie Lyons, Principal, Lum Elementary School

- Roxanne Clement, Bay Farm Elementary Library Media

- Cindy Frankel, Lum Elementary Library Media Teacher

Middle School

- Laurie McLachlan Fry, Principal, Chipman Middle School

High School

- Mike Janvier, Principal, Alameda High School

- Dr. Phil Dauber, Alameda High Department Chair

Community / County Stake Holders

- CTAP Region 4 Tech Plan / Technology Coordinator – Melodee Munckton

- Derrick Starks, Parent, Lum Elementary School

- Ron Mooney, PTA Parent, Franklin Elementary School

- Mike Garneese, MultiMedia Computer Systems

- Steve Walker, ITEON Technologies

- Jane Chisaki, Alameda Free Library, City of Alameda

District Specialty Users

- Luz Casares Chief Financial Officer, Business Services

- Brandon Kruger Chief Human Resource Officer, Human Resources

- Bob DeLuca Director of Maintenance and Operations

- Jane Lee Coordinator of Categorical Programs

The Alameda Unified School District continues to solicit and expand our partnerships with stakeholders to enhance the infusion of educational technology into the curriculum. Our district recognizes that schools alone do not have the resources or expertise to keep pace with rapidly changing technology. We believe that these partnerships will help us serve the growing needs of an increasingly technical and global society.

3.  Curriculum Driven Technology Goals

3a. Description of teachers’ and students’ current access to technology tools both during the school day and outside of school hours.

The following describes the technology access available in classrooms, library/media centers, or labs for all students, including Special Education, GATE, English Language Learners, both during and after school hours. Access to appropriate site-based technology resources has been evaluated through district inventory records, annual California School Survey responses, and CBED data. Teachers and students at all schools have access to technology tools during the school day. Some schools provide students with access before and after school as well as during lunch. The 2006-07 data has been summarized below.

| Alameda Unified School District, Technology by School Type 2006-07 |  |
| --- | --- |
|  | District Students per Computer |
| Elementary | 6.0 |
| Middle | 9.5 |
| High | 5.0 |
| Alternative | 3.4 |
| Source: California Department of Education, Educational Demographics Office (CBEDS0. In addition to computers available for use by students, those used by staff for instructional activities are also included when counting computers at the various schools. This count is then divided by student enrollment to arrive at a students-per-computer figure. |  |

Elementary Schools

| AUSD has 10 elementary schools, ranging in size from 280 to 558 students |  |
| --- | --- |
| All Students, including Special Ed, ELL, and GATE students, have equal access to technology in the following areas: |  |
| Average # of computers in each classroom | 2 |
| Average # of computers in Library/Media Centers | 30 |
| Average # of computers in Computer Labs | 15 |
| Before/After School Hours | Most schools provide 1-2 hours daily |
| Total # of Internet Connected Computers in all 10 schools | 700 |

Middle Schools

| AUSD had 3 middle schools, ranging in size from 604 to 944 students |  |
| --- | --- |
| All Students, including Special Ed, ELL, and GATE students, have equal access to technology in the following areas: |  |
| Average # of computers in Classrooms | 2 |
| Average # of computers in Library/Media Centers | 18 |
| Average # of computers in Computer Labs | 27 |
| Before/After School Hours | Chipman: 1 hour before & 3 hours after school Wood: No access Lincoln: 2 hours after school |
| Total # of Internet Connected Computers | 235 |

Comprehensive High Schools

| Encinal High School enrolls 1,122 students; Alameda High School enrolls 1,914 students |  |
| --- | --- |
| All Students, including Special Ed, ELL, and GATE students, have equal access to technology in the following areas: |  |
| Average # of computers in each classroom | 3 |
| Average # of computers in Library/Media Centers | 43 |
| Average # of computers in Computer Labs | 35 |
| Before/After School Hours | Encinal High: 3 hours after school Alameda High: 30 minutes before school, every lunch hour, 1 ½ hours after school |
| Total # of Internet Connected Computers | 638 |

Island Continuation High School, Grades 10-12

| All Students, including Special Ed, ELL, and GATE students, have equal access to technology in the following areas: |  |
| --- | --- |
| Average # of computers in each Classroom | 0 |
| # of computers in Library/Media Center | 8 |
| # of computers in Computer Lab | 20 |
| Before/After School Hours | 30 minutes before school, 3 hours after school |
| Total # of Internet Connected Computers | 18 |

3b. Description of the district’s current use of hardware and software to support teaching and learning.

The following chart offers a snapshot of the use of technology and information literacy skills as they are integrated in the curriculum in our district. A total of 173 surveys were returned.

Technology Proficiency Reported by all Administrators, Teachers, and Staff Members

Use word processing application 95%

Send and reply to E-mail messages 89%

Ability to load software onto a personal computer 88%

Use search tool to locate information on the Internet 87%

Use desktop publishing or “banner-maker” application 67%

Use spreadsheet or file management application for class record keeping 67%

Coach students on importance of information literacy 59%

Locate lesson resources on Internet and incorporate into curriculum 56%

Discuss larger issues involving student use of technology 49%

Use variety of tech tools and media to advance understanding of ed tech 48%

Able to use a variety of pre-structures courseware 39%

Acknowledged by peers as role model educator 33%

Able to instruct others in application of education tech tools 32%

Am now using tech skills to mentor other teachers 22%

Troubleshoot workstation or network 16%

Utilizing general funds, grant monies, and a community supported bond program, the district has been able to provide technology resources, including hardware and software for curriculum enhancement, administrative support, and community communications.  The following table lists several major components of the district’s technology resources which are available in our classrooms as appropriate for the grade level.

Hardware and software in general use:

| K-12 | Teachers | Students |
| --- | --- | --- |
|  | Individual teacher work station in each classroom: - Microsoft Office 2003 - District email account - SASI Class XP - Measures data warehouse - Internet access, Windows XP - United Streaming - Sucessmaker - Access to School Center web templates - District shared “L” drive - Access to an electronic grading program | Student workstations. - Microsoft Office 2003 - Internet connectivity - United Streaming - Sucessmaker - Appropriate grade level software i.e., Brainpop for 6-8, MathTech 6-8, Kid Pix K-5 - Internet based email |
|  | Other devices: - TVs in all classrooms - Telephone with voicemail in every classroom - Access to networked and local printers - Scanner in every school office - LCD projectors in many classrooms - Digital & video cameras in many classrooms - IPods for podcasting and music education | - TVs in all classrooms - Access to networked and local printers - Scanner in every school office - LCD projectors in many classrooms - Digital & video cameras in many classrooms - IPods for podcasting and music education |

The following table represents the typical frequency and use of technology as it is integrated into the curriculum to support teaching and learning.

| K-12 | Successmaker Used as intervention tool for and skills reinforcement for math, reading, and ELD in before, during, and after school settings. It is the most widely used educational software at the K-8 level. |
| --- | --- |
| K-12 | UnitedStreaming (US) site licenses are being used at all schools. Teachers use US to deliver digital media into student learning environments. Students and caregivers benefit by having at home access to teacher created homework and communication. |
| K-5 | Renzulli GATE students in grades 4/5 have an individual Renzulli Learning license which allows student to pursue independent study projects in school and at home. |
| 6-8 | Brainpop Students and teachers have access at school and home to standards based videos. |
| 6-8 | Student Response Systems: QWIZDOM for Math and Language Arts Intervention and skill building |
| K-12 | Electronic resources aligned with state adopted textbooks |
| K-12 | Groliers on-line electronic resources |
| K-5 | Math Blaster used as intervention and reinforcement for math skills |
| Teachers K-12 | All BTSA teachers have access to My e-Coach.com a tool that allows collaboration, access to electronic resources and professional development. |

3c. Summary of the district’s curricular goals and academic content standards in various district and site comprehensive planning documents.

Alameda Unified School District has established clear curricular goals tied to the academic content standards monitored by various district and site-based assessment systems, and referenced in comprehensive planning documents and efforts. The common underlying purpose of all our district improvement plans is to improve student achievement of the state content standards and to close the predictable achievement gap between the highest and lowest performing ethnic groups.  The technology plan has been developed to support and/or align with the district improvement plans.

##### The following are taken from the AUSD Strategic Plan.

STUDENT SUCCESS

Whatever It Takes!

MISSION

ALAMEDA UNIFIED SCHOOL DISTRICT IS A Team unified to ensure that every school creates a learning environment where every student succeeds.

#### STRATEGIC FOCUS

# Every student will meet or exceed all AUSD and state standards a measured by district and state assessments.

##### CORE VALUES and BELIEFS

We acknowledge, value, and respect the diversity—race, ethnicity, gender, and socioeconomic background—of all students, believing each student’s unique experiences can be used to leverage and maximize student achievement.

We believe the AUSD Graduate Profile Outcomes encompass a common set of skills, knowledge, and attitudes essential to the total development of all Alameda students.  These learning’s have intrinsic value for the fulfillment of each student’s future aspirations.

#### GRADUATE PROFILE OUTCOMES

###### Based on the Graduate Profile

- Achieves state and local standards

- Displays responsibility, self-esteem, self-management, integrity and honesty

- Works well and cooperates with others

- Demonstrates knowledge of career options and the pathway to their attainment

- Applies technology as a tool for learning and career preparation

- Understands and participates in the democratic process

EDUCATIONAL PHILOSOPHY

- Every student has the right to reach his/her full potential

- Development of the whole person—intellectual, emotional, creative, and physical—is an important part of a well-rounded education

- Education is a shared responsibility of the student, the teacher, the parent and the community

- Embracing diversity contributes to the strength of the community

- Instruction should be designed to meet the needs of the diverse learners

- High expectations result in higher achievement

- Students learn best when actively engaged in relevant work

- Community Service is a valuable learning experience for students

- Decision-making must be responsive to student needs

STUDENT ACHIEVEMENT

- Curriculum/Instruction/Assessment

- Strategic Intervention and Support

- Student Involvement and Engagement

- Safe Schools

- Vocational/Career/Adult Education

COMMUNICATIONS and COMMUNITY ENGAGEMENT

- Communications

- Community Engagement

RESOURCES

- Fiscal Resources

- Human Resources

- Community Resources

- Technology

- Facilities

Student Achievement:  Curriculum, Instruction, Assessment

Goal #1 Curricular Coherence & Effective Instruction

FIVE-YEAR GOALS (2003-2008)

(a) Clearly Defined Core Curriculum.  Student achievement is attained through a clearly defined core curriculum that is aligned to state standards and used consistently district-wide.  Teachers, administrators, and support staff are supported through instructional leadership, coaching, evaluation, and collaboration to implement effective educational practices.

(b) Effective Instructional Practices.  Student needs will be addressed through a workable system to identify and implement effective instructional practices across AUSD. These effective practices will include explicit, direct instruction of the skills students need to succeed at each grade level.

(c) Teacher Feedback. Site administrators will provide ongoing feedback to their teachers in the form of problem-solving, data collection, and other assistance so that they can more effectively meet student needs, and reduce or eliminate the achievement gap within AUSD.

Goal #2 Staff Development

FIVE-YEAR GOAL (2003-2008)

Staff Development Aligned with NCLB Teacher Quality Mandates.  All teachers, paraprofessionals, and administrators will be supported in the development of in-depth content knowledge and effective classroom practices through a staff development plan that is aligned to the No Child Left Behind (NCLB) Title II Improving Teacher Quality mandates.

Goal #3:  Staff Recruitment, Assignment, and Retention

### FIVE-YEAR GOAL (2003-2008)

Fully Credentialed, Highly Qualified, Diverse Teachers and Administrators for Every Student.  Every student will be taught by fully credentialed, highly qualified teachers and administrators.  The teacher population will more closely represent the diversity of the student population.

Goal #4 Assessment

FIVE-YEAR GOAL (2003—2008)

Comprehensive Assessment System Supported by Technology.  The success of every student is ensured by the district having a comprehensive assessment system that provides ongoing individual student data that is diagnostic, formative, and summative in nature supported by technology at the classroom, site, and district levels.

Progress on the Academic Performance Index (API) 2006-2007 Reporting Cycle

|  |  |  |  | Ranks |  |  | Targets |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Number of Students Included in the 2006 API | 2006 Base API |  | 2006 Statewide Rank | 2006 Similar Schools Rank |  | 2006-07 Growth Target | 2007 API Target |
| Alameda City Unified | 7,452 | 807 |  | B | B |  | B | B |
| Elementary Schools |  |  |  |  |  |  |  |  |
| Bay Farm Elementary | 361 | 930 |  | 10 | 7 |  | A | A |
| Earhart (Amelia) Elementary | 368 | 900 |  | 10 | 7 |  | A | A |
| Edison Elementary | 248 | 916 |  | 10 | 9 |  | A | A |
| Franklin Elementary | 178 | 913 |  | 10 | 10 |  | A | A |
| Haight Elementary | 298 | 816 |  | 8 | 9 |  | A | A |
| Longfellow Elementary | 115 | 755 |  | 5 | 7 |  | 5 | 760 |
| Lum (Donald D.) Elementary | 342 | 821 |  | 8 | 4 |  | A | A |
| Otis (Frank) Elementary | 240 | 869 |  | 9 | 6 |  | A | A |
| Paden (William G.) Elementary | 266 | 854 |  | 9 | 8 |  | A | A |
| Washington Elementary | 170 | 724 |  | 4 | 3 |  | 5 | 729 |
| Woodstock Elementary | 129 | 787 |  | 7 | 10 |  | 5 | 792 |
| Middle Schools |  |  |  |  |  |  |  |  |
| Chipman Middle | 549 | 688 |  | 4 | 4 |  | 6 | 694 |
| Lincoln Middle | 915 | 872 |  | 10 | 5 |  | A | A |
| Wood (Will C.) Middle | 692 | 757 |  | 7 | 2 |  | 5 | 762 |
| High Schools |  |  |  |  |  |  |  |  |
| Alameda High | 1,348 | 817 |  | 10 | 8 |  | A | A |
| Arthur Anderson Community Learning Cente | 176 | 852 |  | 10 | 8 |  | A | A |
| Encinal High | 714 | 714 |  | 6 | 8 |  | 5 | 719 |
| Small Schools |  |  |  |  |  |  |  |  |
| Alameda Science and Technology Institute | 57 | 877 * |  | 10 * | N/A |  | A | A |
| Bay Area School of Enterprise | 47 | 667 * |  | 4 * | N/A |  | 7 | 674 |
| Miller (George P.) Elementary | 89 | 753 * |  | 5 * | N/A |  | 5 | 758 |
| ASAM Schools |  |  |  |  |  |  |  |  |
| Island High (Continuation) | 46 | 566 * |  | B | B |  | B | B |

3d. List of clear goals and a specific implementation plan for using technology to improve teaching and learning by supporting the district curricular goals and academic content standards.

The Alameda Unified School District has just completed a new History and Social Science adoption.  In addition we are in the process of selecting a new Science followed by Language Arts and Math courses of studies.  All of these new curriculums have significant technology components attached to them for both students as well as teacher use.  While we will concentrate our efforts on language arts and math, the requirements to implement other new curricilum will necessitate a concerted effort in planning and implementing staff development, technology upgrades and curriculum support at the K-8 level.

Goal 3d.1: Teachers will use technology to improve instruction and to assist students in meeting state Language Arts, Social Studies and Math content standards.

Objective 3d.1: By June 2010, on a daily basis 95% of all teachers will use technology for instruction in Language Arts, Social Studies and Math to assist students in meeting state content standards and district curricular goals.

Year 1 Benchmark: By June 2008, at least once a week 75% of all teachers will use technology for instruction and to assist students in meeting state content standards and district curricular goals.

Year 2 Benchmark: By June 2009, two-three times a week 85% of all teachers will use technology for instruction and to assist students in meeting state content standards and district curricular goals.

Year Benchmark: By June 2010 on a daily basis 95% of all teachers will use technology for instruction and to assist students in meeting state content standards and district curricular goals.

| Person(s) Responsible 1. Principals 2.District Assessment Coordinator 3.Director of Technology 4.Site Technology Coordinators 5.Teachers 6.Director of Curriculum and Instruction 7.Technology TOSA 8.Media Specialists |  |  |  |
| --- | --- | --- | --- |
| Implementation Activities | Person(s) Responsible | Start & Completion Years |  |
| K-5 Teachers will use electronic resources aligned to Houghton Mifflin Reading Program to support Language Arts standards. | 3,5,6 | 2007 | 2010 |
| K-8 Teachers will develop lessons using electronic resources included with the adopted Language Arts textbooks and materials. | 5,7,8 | 2008 | 2010 |
| 4-8 ELL teachers will use electronic resources aligned with Hampton Brown High Point to deliver intensive support in language acquisition. | 1,5,6 | 2008 | 2010 |
| 4-8 Teachers will use electronic resources from the SRA Reach Program for intensive intervention in Language Arts instruction for at-risk students. | 2,5 | 2007 | 2010 |
| K-5 Teachers will use the Scott Foresman Digital Pathway as part of their weekly social studies lessons | 4,5,6 | 2007 | 2010 |
| Each K-5 school will have a technology support teacher trained to provide hands-on support in the successful use of the Scott Foresman Digital Pathway Social Studies electronic resources. | 6,7 | 2007 | 2008 |
| K-12 Teachers will use electronic resources aligned with math textbooks to reinforce student acquisition of math skills. | 2,6,7 | 2007 | 2010 |
| 6-8 Teachers will use CTAP Middle School Math Project to align curriculum with electronic resources | 4,5,7 | 2007 | 2010 |
| K-5 Teachers will use the electronic resources aligned with the science textbook to be adopted in Fall 2008 to support student learning | 3,5,6 | 2008 | 2010 |
| K-5 Site technology lead teachers will provide hands on support for the use of science electronic resources. | 4,5,6 | 2008 | 2010 |
| 6-8 Science teachers will use the electronic resources aligned with the adopted science textbook to support student learning. | 5,6,7 | 2007 | 2010 |
| 6-8 Science teachers will have access to a mobile multi-media presentation cart (LCD projector and computer) to deliver lessons electronically. | 3,5 | 2007 | 2010 |
| K-12 Teachers will create, store, share and access technology integrated lessons organized by subject through district website. | 4,5,6 | 2008 | 2010 |
| K-12 Teachers will use SuccessMaker software to bridge the gaps in specific skill areas for students needing intervention and skill building in Language Arts and Math. | 1,5,7 | 2007 | 2010 |
| 6-8 Teachers will use Qwizdom (Student Response System) for immediate feedback, student engagement and data analysis in delivering of Math and Language Arts standards. | 2,5,7 | 2007 | 2010 |
| 1. Principals 2.District Assessment Coordinator 3.Director of Technology 4.Site Technology Coordinators 5.Teachers 6.Director of Curriculum and Instruction 7.Technology TOSA 8.Media Specialists |  |  |  |

Goal 3d: To improve student learning through technology rich instruction

Objective 3d.2: Technology will be used to support teaching and learning on a daily basis so that 95% of all students will meet the grade level content standards in Language Arts, Social Studies, Math and Science by 2010.

Year 1 Benchmark: Technology will be used at least once a week to support teaching and learning so that 50% of all students will meet grade level Language Arts, Social Studies, Math and Science content standards by June 2008.

Year 2 Benchmark: Technology will be used two-three times a week to support teaching and learning so that 75% of all students will meet grade level Language Arts, Social Studies, Math and Science content standards by June 2009.

Year 3 Benchmark: Technology will be used to support teaching and learning on a daily basis so that 95% of all students will meet grade level Language Arts, Social Studies, Math and Science content standards by June 2010.

| Person(s) Responsible 1. Principals 2.District Assessment Coordinator 3.Director of Technology 4.Site Technology Coordinators 5.Teachers 6.Director of Curriculum and Instruction 7.Technology TOSA 8.Media Specialists |  |  |  |
| --- | --- | --- | --- |
| Implementation Activities | Person(s) Responsible | Start & Completion Years |  |
| K-5 Students will access electronic resources aligned to Houghton Mifflin Reading Program to support Language Arts standards. | 1,2,3,5,6 | 2007 | 2010 |
| K-8 Students will access lessons developed by teachers using electronic resources to support their understanding of the adopted Language Arts textbooks and materials. | 1,5,7,8 | 2007 | 2010 |
| 4-5 GATE students have Renzulli Learning accounts to pursue independent projects at home and school. | 1,4,5,6 | 2007 | 2010 |
| 4-8 ELL learners access electronic resources aligned with Hampton Brown High Point to receive intensive support in language acquisition. | 1,5,6 | 2008 | 2010 |
| 4-8 at-risk students will use electronic resources from the SRA Reach Program for intensive intervention in Language Arts instruction. | 1,2,5,6 | 2007 | 2010 |
| K-5 Students will access the Scott Foresman Digital Pathway as part of their weekly social studies lessons. | 1,4,5,6 | 2007 | 2010 |
| K-5 Students will benefit by having a technology support teacher trained to provide support in the successful use of the Scott Foresman Digital Pathway electronic resources. | 4,5,7 | 2007 | 2008 |
| K-12 Students will use electronic resources aligned with the state adopted math textbooks to reinforce their acquisition of grade appropriate math skills. | 2,6,7 | 2007 | 2010 |
| 6-8 Students will use CTAP Middle School Math Project online resources to receive supplemental support with textbook instructional materials. | 4,5,7 | 2007 | 2010 |
| 6-8 Students will have access to the EETT MathTech program which provides an extra period of math intervention using content reinforcement through electronic resources. | 1,5,7 | 2007 | 2010 |
| K-5 Students will access electronic resources aligned with the science textbook to be adopted in Fall 2007. | 1,2,3,5,6 | 2007 | 2010 |
| K-5 Students will receive support from site technology lead teachers in the use of science electronic resources. | 1,4,5,6 | 2008 | 2010 |
| 6-8 Students will receive access to multi-media presentations through teachers’ use of a mobile multi-media cart to support electronic science curriculum. | 3 | 2007 | 2010 |
| K-12 Students needing intervention and skill building in Language Arts and Math will use SuccessMaker software to bridge the gaps in specific skill areas. | 1,5,7 | 2007 | 2010 |

| 6-8 Students will use Qwizdom (Student Response System) for immediate feedback, active engagement and skill building in Math and Language Arts standards. | 2,4,5,7 | 2007 | 2010 |
| --- | --- | --- | --- |
| 1. Principals 2.District Assessment Coordinator 3.Director of Technology 4.Site Technology Coordinators 5.Teachers 6.Director of Curriculum and Instruction 7.Technology TOSA 8.Media Specialists |  |  |  |

| Evaluation Instrument(s): Data To Be Collected & Analysis Process | Schedule for Collection and Evaluation | Person(s) Responsible |
| --- | --- | --- |
| EdTechProfile | Annually | 1,3,5 |
| Teacher created Technology Integrated Lesson Bank | Annually | 1,5,6 |
| State and district-wide assessments | Annually | 1, 3, 5 |
| Student work | Trimester | 1,5 |

3e. List of clear goals and a specific implementation plan as to how and when students will acquire technology and information literacy skills needed to succeed in the classroom and the workplace.

Alameda will implement the Information and Communications Technology (ICT) Literacy framework for students K-12. We will use the ICT maps in English and  Math to guide our district’s implementation of the 21st Century Learning skills.

Goal 3e: Students will acquire and use Information and Communications Technology literacy (ICT) skills needed in the 21st Century.

Objective 3e.1: By June 2010 75% of students acquire and use ICT as identified in the 21st Century Learning Skills to develop content knowledge and skills.

Year 1 Benchmark: By June 2008 25% of students will acquire and use ICT as identified in the 21st Century Learning Skills to develop content knowledge and skills.

Year 2 Benchmark: By June 2009 50% of students will acquire and use ICT as identified in the 21st Century Learning Skills to develop content knowledge and skills.

Year 3 Benchmark: By June 2010 75% of students will acquire and ICT as identified in the 21st Century Learning Skills to develop content knowledge and skills.

| Person(s) Responsible 1. Principals 2.District Assessment Coordinator 3.Director of Technology 4.Site Technology Coordinators 5.Teachers 6.Director of Curriculum and Instruction 7.Technology TOSA 8.Media Specialists |  |  |  |
| --- | --- | --- | --- |
| Implementation Activities | Person(s) Responsible | Start & Completion Years |  |
| K-12 Media Specialists will become familiar with and incorporate the 21st Learning Skills into the planning of their monthly meetings. | 5,8 | 2007 | 2010 |
| K-12 students will learn Information and Communications Technology literacy ICT skills under the supervision of Media Specialists in their weekly Media Center visits. | 4,5,7,8 | 2007 | 2010 |
| K-8 Language Arts teachers will begin to incorporate ICT Literacy Maps activities into Language Arts lessons. | 4,5,7,8 | 2008 | 2010 |
| K-12 Math, Science teachers will develop lessons that incorporate in the ICT map activities in their instruction. | 4, 5, 6, 8 | 2009 | 2010 |
| K-8 Students will create projects based on ICT map activities. | 4,8 | 2009 | 2010 |
| 4-12 Select students will be trained as part of the “ICT Crew” to act as the first line of technology support in the schools. | 1,3,4,7,8 | Fall 2007 | 2010 |

| Evaluation Instrument(s): Data To Be Collected & Analysis Process | Schedule for Collection and Evaluation | Person(s) Responsible |
| --- | --- | --- |
| The Ed Tech Student Technology Use Survey will be administered every Spring and Fall as a pre / post evaluation of the student’s technology literacy skills | Spring, Fall ( yearly ) | 3,4,5,7 |
| Samples of student work demonstrating the use of ICT skills will be evaluated | Ongoing collection Spring evaluation | 4, 5, 6,8 |
| PASS (Performance-based) Assessments address the 21st Century thinking and learning skills. AUSD will use PASS at the 6-8 level as a portfolio style evaluations ( All AUSD 6th graders create a portfolio that represents their Middle School experience from 6th grade through 8th grade. | Late Spring End of year evaluations of portfolios | 1,2,4, 5, 6,8 |
| 1. Principals 2.District Assessment Coordinator 3.Director of Technology 4.Site Technology Coordinators 5.Teachers 6.Director of Curriculum and Instruction 7.Technology TOSA 8.Media Specialists |  |  |

Goal 3f.1: All students will have access to technology appropriate to their learning needs.

Objective 3f.1 By June 2010 all students will have access to technology appropriate to their learning needs.

Year 1 Benchmark: By June 2008 all special education students will have the adaptive,assistive devices and technology tools as identified with their IEP

Year 2 Benchmark By June 2009, all EL students will have additional language acquisition software. GATE students will have access to additional technologies that meet their learning needs. Teachers will learn technology-based strategies to meet their learning needs..

Year 3 Benchmark By June 2010, AUSD will provide expanded access (on and off campus) to students with no technology within the home, and all students will have access to technology appropriate to their learning needs

| Person(s) Responsible 1. Principals 2.District Assessment Coordinator 3.Director of Technology 4.Site Technology Coordinators 5.Teachers 6.Director of Curriculum and Instruction 7.Technology TOSA 8.Media Specialists |  |  |  |
| --- | --- | --- | --- |
| Action Steps for Objective 3f.1: | Person(s) Responsible | Start & Completion Years |  |
| Conduct an annual inventory of of classroom technology, including classrooms serving students with special needs. | 1, 4, 5 | 2007 | 2010 |
| Try to achieve a 4:1 ratio of student to multimedia/Internet-capable computing devices for all students, including those in Special Education , GATE and English Language Learner Programs. | 3, | 2008 | 2010 |
| Provide all students a baseline package of reliable technology to support the district's curriculum goals and academic content standards | 1,4,5 | 2007 | 2010 |
| Appoint representatives from Special Ed, GATE and ELL to work with Media Specialists to ensure the needs of their students are met | 1,2, | 2007 | 2010 |
| Review all existing IEPs to identify adaptive and assistive devices needed | 3,7 | 2007 | 2010 |
| Students, including ELL, will have access to technology resources such as talking text, web resources, graphic organizers, and modification techniques to scaffold learning to meet their needs | 3,5 | 2008 | 2010 |
| Continue to provide desktop computers to local public library for AUSD students to access district online resources (UnitedStreaming, BrainPop, SuccessMaker etc) outside school hours. | 3,7 | 2008 | 2010 |
| Identify and post on the district website technology resources appropriate to all students including special education , GATE and ELL students | 4,6 | 2007 | 2010 |
| Schools will continue to provide student access to technology resources before, during and after-school | 1,4 | 2007 | 2010 |

| Evaluation Instrument(s): Data To Be Collected & Analysis Process | Schedule for Collection and Evaluation | Person(s) Responsible |
| --- | --- | --- |
| Student IEPs, AUSD GATE list, ELL Assessments | Ongoing | 1, 3, 5 |
| Referrals from district personnel for loaner equipment | Ongoing | 1, 2, 3, 4, 5, 6, |

| Goal 3g: Teachers will utilize technology to support student record keeping, access student assessment data, and administer formative assessments in order to support their efforts to meet individual student academic needs. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Objective 3g.1: By June 2010, 80% of teachers at grades 4-12 will be proficient in using a district-supported grade program and report card program that supports their efforts to meet individual student needs. |  |  |  |  |
| Year 1 Benchmark 3g.1: By June 2008, the district will have chosen a grading program and report card program that interfaces with the student database. |  |  |  |  |
| Year 2 Benchmark 3g.1: By June 2009, 50% of teachers at grades 4-12 will be proficient in using the district supported grade and report card program(s) to support their efforts to meet individual student needs. |  |  |  |  |
| Year 3 Benchmark 3g.1: By June 2010, 80% of teachers at grades 4-12 will be proficient in using the district supported grade and report card program(s) to support their efforts to meet individual student needs. |  |  |  |  |
| Person(s) Responsible 1. Principals 2.District Assessment Coordinator 3.Director of Technology 4.Site Technology Coordinators 5.Teachers 6.Director of Curriculum and Instruction 7.Technology TOSA 8.Media Specialists |  |  |  |  |
| Action Steps for Objective 3g.1: | Person(s) Responsible | Start & Completion Years |  |  |
| Explore grading software for student tracking such as, Integrade Pro, MyGradeBook.com, SASI grading module | 1,2,3, 7 | 2008 | 2008 |  |
| Explore online report card options including Measures. Look for integration with grading software and student database | 1,2,3,7 | 2008 | 2008 |  |
| Create and implement process for choosing integrated system for grades and report cards | 1,2,3,7 | 2008 | 2008 |  |
| Train teachers in use of program | 1,2,3,7 | 2008 | 2010 |  |
| Objective 3.g.2: by June, 2010, 90% of teachers will be proficient in using the district student achievement database (Measures) to access student assessment data that supports their efforts to meet individual student needs. |  |  |  |  |
| Year 1 Benchmark: By June 2008, 65% of teachers will be proficient in using the district student achievement database to access student assessment data that supports their efforts to meet individual student needs. |  |  |  |  |
| Year 2 Benchmark: By June 2009, 80% of teachers will be proficient in using the district student achievement database to access student assessment data that supports their efforts to meet individual student needs. |  |  |  |  |
| Year 3 Benchmark: By June 2010, 90% of teachers will be proficient in using the district student achievement database to access student assessment data that supports their efforts to meet individual student needs. |  |  |  |  |

| Implementation Activities | Person(s) Responsible | Start & Completion Years |  |
| --- | --- | --- | --- |
| Continue to support Assessment Liaisons from each K-5 site with training in using the Measures database for accessing data to guide instruction. | 2,6 | 2008 | 2010 |
| Continue to support Lit lead teachers and Literacy/math coaches (K-12) with training in using the Measures database for accessing data to guide instruction. | 2, 6 | 2008 | 2010 |
| Continue to offer district wide training in using the Measures database for accessing data to guide instruction | 2,7 | 2008 | 2010 |
| Offer grade/subject specific training at sites in using the Measures database for accessing data to guide instruction | 1,2,6 | 2008 | 2010 |
| Objective 3.g.3: by June, 2010, 95% of grade 4-9 teachers will be proficient in administering formative assessments online and generating online reports of assessment results that support their efforts to meet individual student needs. |  |  |  |
| Year 1 Benchmark: By June 2008, 50% of grade 4-9 teachers will be proficient in administering formative assessments online and generating online reports of assessment results that support their efforts to meet individual student needs. |  |  |  |
| Year 2 Benchmark: By June 2009, 70% of grade 4-9 teachers will be proficient in administering formative assessments online and generating online reports of assessment results that support their efforts to meet individual student needs. |  |  |  |
| Year 3 Benchmark: By June 2010, 90% of grade 4-9 teachers will be proficient in administering formative assessments online and generating online reports of assessment results that support their efforts to meet individual student needs. |  |  |  |

| Person(s) Responsible 1. Principals 2.District Assessment Coordinator 3.Director of Technology 4.Site Technology Coordinators 5.Teachers 6.Director of Curriculum and Instruction 7.Technology TOSA 8.Media Specialists |  |  |  |
| --- | --- | --- | --- |
| Implementation Activities | Person(s) Responsible | Start & Completion Years |  |
| Increase the number of grade 4-12 district wide formative assessments available online to 80% | 2,6 | 2007 | 2010 |
| Continue to train all Literacy/math coaches, media center teachers, site tech coordinators, and computer lab paraprofessionals to support online testing. | 2,3,4,7 | 2007 | 2010 |
| 6-8 Teachers will use Qwizdom (Student Response System) for immediate feedback, and formative assessments in Math and Language Arts. | 2,5,7 | 2007 | 2010 |
| Train teachers at time of need to provide online testing. | 2,4,7 | 2008 | 2010 |
| Continue to provide time-of-need support to teachers who use online testing. | 2,7 | 2008 | 2010 |
| Work with school leadership teams to voluntarily increase the use of online testing and use of online assessment reports. | 1,2,5 | 2008 | 2010 |
| Increase the number of assessments that are required online as the capacity of school labs (networked computers) makes this possible | 1,2,3,4 | 2009 | 2010 |
| Evaluation Instrument(s): Data To Be Collected & Analysis Process | Schedule for Collection and Evaluation | Person(s) Responsible |  |
| Tech committee and sub-committee meeting agendas and notes | At least quarterly | 2,3 |  |
| Tech services and Assessment Department professional development logs/sign-in sheets | Collected in each PD session; evaluated semi-annually | 2,3,7 |  |
| District formative assessment data from Measures | Quarterly | 2 |  |
| CST Mathematics, Language Arts, and CAHSEE Exam scores | Evaluated annually | 2 |  |
| 1. Principals 2.District Assessment Coordinator 3.Director of Technology 4.Site Technology Coordinators 5.Teachers 6.Director of Curriculum and Instruction 7.Technology TOSA 8.Media Specialists |  |  |  |

| Goal 3h: List of clear goals and a specific implementation plan to utilize technology to make teachers and administrators more accessible to parents |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objective 3h.1: By June 2010, 80% of all schools will offer parents password protected, online access to their student’s attendance, assignments and grades through a web-based interface for parents and students, such as SASIxp’s Parent Connect |  |  |  |  |  |  |
| Year 1 Benchmark 3h.1: By June 2008, the district will have chosen a web-based interface for parent and students access that interfaces with the student database. |  |  |  |  |  |  |
| Year 1 Benchmark 3h.1: By January 2009, 50% of AUSD middle and high schools will offer parents password protected, online access to their student’s attendance, discipline records, assignments and grades through a web-based system such as SASIxp’s Parent Connect. |  |  |  |  |  |  |
| Year 2 Benchmark 3h.1: By June 2009, 50% of all school sites will be posting student attendance, assignments and grades online for parent access |  |  |  |  |  |  |
| Year 3 Benchmark 3h.1: By June 2010, 80% of all school sites will be posting student attendance, assignments and grades online for parent access |  |  |  |  |  |  |
| Action Steps for Objective 3h.1: |  | Person(s) Responsible |  |  | Start & Completion Years |  |
| Research, evaluate and select the appropriate web-based communications package |  | 3,4,7 |  |  | 2007 | 2008 |
| Ensure all district schools have the hardware, infrastructure, and training needed to implement the web-based communications package |  | 3,4,7 |  |  | 2007 | 2009 |
| Provide MS Front Page, DreamWeaver and SchoolCenter web publishing software training opportunities for teachers and administrators to publish / communicate school and teacher information, activities and assignments on their school web site. |  | 3,4,7 |  |  | 2007 | 2010 |
| Provide parent training on the District’s selected web-based communications package |  | 1,3,7 |  |  | 2007 | 2010 |
| Objective 3.h.2: by June, 2010, 95% of all district site administrators and teachers will provide parents with timely school / class information via newsletters, flyers sent via email, also posted on the Internet at the school web site |  |  |  |  |  |  |
| Year 1 Benchmark: By June 2008, 35% of site administrators and teachers will be proficient in using e-mail and electronic resources to send electronic information home to parents |  |  |  |  |  |  |
| Year 2 Benchmark: By June 2009, 70% of site administrators and teachers will be proficient in using e-mail and electronic resources to send electronic information home to parents |  |  |  |  |  |  |
| Year 3 Benchmark: By June 2010, 95% of site administrators and teachers will be proficient in using e-mail and electronic resources to send electronic information home to parents |  |  |  |  |  |  |
| Action Steps for Objective 3h.2: | Person(s) Responsible |  | Start & Completion Years |  |  |  |
| By June 2008 provide Word and Desktop publishing training to teachers and classified staff to learn to publish professional / attention getting documents to improve communication between home, school, and community | 3,7 |  | 2007 | 2008 |  |  |
| By June 2008, develop an Outlook Exchange district wide training program for all teacher and administrators | 3,7 |  | 2007 | 2008 |  |  |
| Evaluation Instrument(s): Data To Be Collected & Analysis Process | Schedule for Collection and Evaluation |  | Person(s) Responsible |  |  |  |
| Tech committee and sub-committee meeting agendas and notes | At least quarterly |  | 2,3 |  |  |  |
| Tech services and Assessment Department professional development logs/sign-in sheets | Collected in each PD session; evaluated semi-annually |  | 2,3,7 |  |  |  |
| The District Technology Director, school site administrators and site technology coordinators will track the development and implementation of all activities and accomplishments quarterly and report progress at our quarterly district/ site admin meetings. | Quarterly Technology Steering Meetings |  | 3,7 |  |  |  |
| 1. Principals 2.District Assessment Coordinator 3.Director of Technology 4.Site Technology Coordinators 5.Teachers 6.Director of Curriculum and Instruction 7.Technology TOSA 8.Media Specialists |  |  |  |  |  |  |

The Assistant Superintendent of Business Services, Director of Technology, and Site Technicians from each school will meet monthly to review goals, objectives and progress on the Technology Plan. Site administrators will also meet monthly to review the progress on the Technology Plan.

Both of the aforementioned groups will The Assistant Superintendent of Business Services, Director of Technology, and Site Technicians from each school meet monthly to review issues, upcoming deadlines, and progress on the Technology Plan. This advisory committee monitors site and District budget issues.

The aforementioned group will prepare an annual report for presentation to the Superintendent and School Board.

Professional Development

4a. Summary of AUSD Teachers’ & Administrators’ Technology Skills

Our AUSD Education Technology Plan provides a clear summary of our district teachers’ and administrators’ current technology skills. Our survey findings are summarized by discrete skills in order to better facilitate professional development planning that meets our identified needs and technology plan goals. Additional district technology integration data can be found in Component 3b of our Educational Technology Plan.

Our district reviews the EdTech Profile survey data and teacher input annually in the fall to plan for district sponsored professional development activities for the year. Schools use their site’s EdTech Profile survey data and teacher input annually to plan for site-based professional development needs.  As a portion of the support for teachers and professional development, the District is hiring a Teacher on Special Assignment. One of our goals for that position is to perform district reviews of the EdTech Profile data and plan for district sponsored professional development activities for the duration of this plan.

Currently, the Technology Services Training Center provides ongoing staff development utilizing hardware and software that is available to teachers at their sites and in their classrooms.  District Technology Services staff members provided in-service trainings to sites supporting the implementation of SASIxp Classroom (online attendance) for daily assessment record keeping and for the generation of progress and grade reports.  District Technology Services staff members and site based trainers, also provide ongoing workshops at the Technology Training Lab for teachers and staff on the district’s common operating environment software, web development and data software, and assessment software as well as computer based classroom software such as SuccessMaker, MathTech United Streaming, BrainPop and the new History, Social Science and Science adoptions.

The district believes that teachers and administrators need professional development opportunities and the time to develop and practice the necessary skills to become proficient technology using educators. In an effort to have every teacher and administrator meet the level II professional proficiencies, as identified on the EdTech Profile, by 2010, the district will create a Training of Trainers program that will be directed by the Teacher on Special Assignment. This program will consist of elementary, middle and high school teachers interested in teacher training and staff development. These teachers will participate in up to 10 hours of training designed to enable them to provide 10 hours of training at their school sites. This training will be aligned to the professional teacher’s proficiency in Computer-Based Technology standards detailed in the California Commission on Teacher Credentialing Standards 9 and 16 – (for the Multiple and/or Single Subject Teaching Credential) Using Technology to Support Student Learning.  Hardware and software necessary to perform the required training at the sites will be provided to the teachers.

AUSD  Survey Data

Staff Proficiency data of AUSD school site administrator’s indicates that most administrators are at the intermediate level or slightly higher with general computing, Internet, e-mail, word processing and presentation skills; spreadsheets, database skills and hardware knowledge are at a level lower that basic .

Summary of Staff Proficiency  ( all staff members, admin and teachers  )

- Use word processing application							95%

- Send and reply to E-mail messages						89%

- Ability to load software onto a personal computer				88%

- Use search tool to locate information on the Internet				87%

- Use desktop publishing or “banner-maker” application				67%

- Use spreadsheet or file management application for class record keeping	67%

- Coach students on importance of information literacy				59%

- Locate lesson resources on Internet and incorporate into curriculum		56%

- Discuss larger issues involving student use of technology			49%

- Use variety of tech tools and media to advance understanding of ed tech	48%

- Able to use a variety of pre-structures courseware				39%

- Acknowledged by peers as role model educator					33%

- Able to instruct others in application of education tech tools			32%

- Am now using tech skills to mentor other teachers				22%

- Troubleshoot workstation or network						16%

AUSD Teachers’ Survey Data

EdTech Profile data of AUSD teachers as of  03/13/2007, indicates that most teachers are at intermediate or better levels with general computing, Internet, e-mail, word processing, and only slightly lower  in  presentation, spreadsheet, and database skills.

Teachers need ongoing maintenance levels of professional development opportunities in basic personal technology proficiencies.  Additional professional development will be available for increased knowledge and functionality of the suites of software available to the teachers.

| 1 | General computer knowledge and skills (Includes 175 in calculation) |
| --- | --- |
| 2 | Internet skills (Includes 175 in calculation) |
| 3 | Email skills (Includes 175 in calculation) |
| 4 | Word processing skills (Includes 175 in calculation) |
| 5 | Presentation software skills (Includes 173 in calculation) |
| 6 | Spreadsheet software skills (Includes 172 in calculation) |
| 7 | Database software skills (Includes 172 in calculation) |

4b-d. Professional Development Goals, Benchmarks, Timelines, Monitoring, and Evaluation.

All of the Professional Development Criteria 4b-d elements are included in the teachers’ and administrators’ professional development action plan charts in the Component 4 pages that follow. Our professional development action plans are based on a thorough needs analysis and include clear, specific, realistic goals, and measurable objectives that will provide our teachers and administrators with sustained, ongoing professional development necessary to implement the Curriculum Component of our Education Technology Plan.

Our three main Education Technology professional development goals over the next five years are:

Goal 1: AUSD site administrators and teachers will become proficient with the same general technology skills, technology integration skills, and information literacy skills required of their students as well as proficient with work specific productivity tools.

Goal 2: AUSD site administrators and teachers district will become proficient in the use of technology to improve student achievement data collection, analysis, reporting, and decision making.

Goal 3: AUSD site administrators and teachers will become proficient in the use of technology to improve two-way communication between home and school.

Our Education Technology Professional development will encompass a three tiered professional development approach based on teachers’ and administrators’  individual technology training need.

  - Annually as needed, we will offer Personal proficiency training on ICT’s skills including general computer knowledge and skills; Internet skills; Email skills; Word processing skills; Presentation software skills; and Spreadsheet /Database software skills.

  - Annually as needed, we will offer Professional proficiency training on ICT’s skills integration including information literacy, curriculum-based software, SBE adopted electronic resources, online resources such as SETs, and job specific productivity and assessment tools.

  - Annually as needed, we will offer Technology Leadership / Coach Proficiency training: Training interested teachers as site-based coaches offering support to teachers as they work toward proficiency in tiers one and two.

Our coordinated professional development plan is based on the analysis of our teachers’ and administrators’ technology skills needs as well as our district’s curricular goals. The district will offer a variety of training options such as the CTAP Online

( www.ctaponline.org ) learning portal, face-to-face training & collaboration time, and one-on-one coaching. We will maximize the use of technology and site resources to support the district’s goals and objectives for curriculum, instruction, intervention, and assessment, including but not limited to the following:

- District sponsored technology coaches and CTAP Online mentors available to school sites.

- Annual face-to-face technology skill professional development opportunities.

- Anytime, anywhere online district technology professional development opportunities using CTAP Online Personal and Professional Proficiency technology classes and supported by site based technology coaches.

- District content and grade-band specific technology integration face-to-face professional development supported with district professional development and resources online using CTAP On line’s Course Builder tool.

- CTAP Online technology integration training.

- Broad-based completions of the EdTech Profile survey and professional development data analysis to track improvements and training needs.

- Annual professional development offerings / priorities based on student, teacher, and administrator EdTech Profile assessment survey data and district curricular goals.

- Student assessment and intervention, student information system, web publishing, e-mail, and voice-mail training opportunities for all stakeholders as needed to support student achievement and improve home / school communications and interventions.

- Identification, training, and use of low and no cost Internet, video-conferencing and face-to-face learning opportunities and resources.

- National, State and local online research-based strategies and resources will be leveraged and integrated during faculty meetings, collaboration time, and professional development such as: the U.S. Department of Education’s web site What Works Clearinghouse (http://www.w-w-c.org/).

- We will also rely on the Alameda County Office of Education, CTAP Region 4, and CTAP Online resources, and the Statewide Education Technology Services (SETS) which includes: California Learning Resource Network (CLRN)- which identifies CDE approved supplemental electronic learning resources that both meet local instructional needs and embody the implementation of California curriculum frameworks and standards; the Technology Information Center for Administrative Leadership (TICAL) - which helps administrators find technology resources to assist in the day-to-day needs of their jobs; and the Technical Support for Education Technology in Schools (TechSETS) - which provides technical professionals in California schools improved access to training, support and other resources.

#### AUSD Professional Development Plan July 1, 2007 – June 30, 2010 (sections 4b-4d)

| Goal 4.1 AUSD site administrators and teachers will become proficient with the same general technology skills, and information literacy skills required of students as well as proficient with work specific productivity tools. |  |  |  |
| --- | --- | --- | --- |
| Objective 4.1a By June 2010, 65% of AUSD site administrators and teachers, will participate in district sponsored educational technology professional development, and will become proficient with general technology knowledge and skills, information literacy, and productivity tools aligned to EdTechProfile. |  |  |  |
| Year 1 Benchmark By June 2008, 25% of AUSD site administrators and teachers, will participate in district sponsored educational technology professional development, and will become proficient with general technology knowledge and skills, information literacy, and productivity tools aligned to EdTechProfile. |  |  |  |
| Year 1 Benchmark By June 2009, 45% of AUSD site administrators and teachers, will participate in district sponsored educational technology professional development, and will become proficient with general technology knowledge and skills, information literacy, and productivity tools aligned to EdTechProfile. |  |  |  |
| Year 1 Benchmark By June 2010, 65% of AUSD site administrators and teachers, will participate in district sponsored educational technology professional development, and will become proficient with general technology knowledge and skills, information literacy, and productivity tools aligned to EdTechProfile. |  |  |  |
| Objective 4.1 b By June 2010, 65% of AUSD ELA, Social Studies, and Math teachers, will participate in professional development to develop proficieies in technology integration and information literacy skills aligned to EdTechProfile Standards 9 & 16 as well as the 21st Century Information and Communications Technology Literacies . These will include coaching in critical thinking,; creativity and integration ; and collaborative skills as defined by the ICT framework.. |  |  |  |
| Year 1 Benchmark By June 2008, 25% of AUSD ELA, Social Studies, and Math teachers, will participate educational technology integration professional development and will become proficient with technology integration and information literacy skills aligned to EdTechProfile Standards 9 & 16 as well as the 21st Century Information and Communications Technology Literacies. |  |  |  |
| Year 2 Benchmark By June 2009, 45% of AUSD ELA, Social Studies, and Math teachers, will participate educational technology integration professional development and will become proficient with technology integration and information literacy skills aligned to EdTechProfile Standards 9 & 16 as well as the 21st Century Information and Communications Technology Literacies. |  |  |  |
| Year 3 Benchmark By June 2010, 65% of AUSD ELA, Social Studies, and Math teachers, will participate educational technology integration professional development and will become proficient with technology integration and information literacy skills aligned to EdTechProfile Standards 9 & 16 as well as the 21st Century Information and Communications Technology Literacies. |  |  |  |
| Implementation Activities | Person(s) Responsible | Start | Completion |
| ## Annually in the spring, require administrator and teacher completion of EdTech Profile survey by all who participate in district sponsored EETT technology training programs during the school year, and all others who have not completed a survey within the past 18 months. | 3,7 | 2007 | 2010 |
| ## Annually in June, analyze EdTechProfile administrator and teacher technology and integration skill data to plan for professional development offerings during the year. | 3,7 | 2007 | 2010 |
| Annually as needed, provide ICT workshops to teachers, administrators, and media specialists | 3,7 | 2008 | 2010 |
| Annually in the fall, schedule and promote district sponsored technology integration and CLRN approved curriculum-based software and resource workshops aligned to the adopted textbooks: - Year 1 -ELA teachers - Year 1 - K-5 Social Studies - Year 1 - 6-8 Science - Year 2 – K-5 Science - Year 3 – K-5 Math | 3,6,7 | 2007 2007 2007 2008 2009 | 2010 2010 2010 2010 2010 |
| Annually, the district will train site-based technology integration mentors and CTAP Online mentors to support district technology participants at the site level. | 3,7 | 2007 | 2010 |
| K-12 teachers will be trained on how to create, store and access technology integrated lessons to be stored on district website. | 7 | 2008 | 2010 |
| K-12 teachers will be trained on the implementation of SuccessMaker in ELA and math. | 7 | 2007 | 2010 |
| 6-8 teachers will receive training on the Qwizdom, student response system. | 7 | 2007 | 2010 |
| ELL teachers will be trained in technology resources such as talking text, web resources, and graphic organizers. | 7 | 2008 | 2010 |

| Goal 4.2 AUSD site administrators and teachers will become proficient in the use of technology to improve student achievement data collection, analysis, reporting, and decision making |  |  |  |
| --- | --- | --- | --- |
| Objective 4.2 By June 2010, 75% of AUSD teachers will attend professional development, and will be proficient in the use of technology (such as Measures and / or Electronic Gradebooks, spreadsheets) to analyze student assessment data and make data-driven decisions to meet individual student academic needs and target student intervention needs. |  |  |  |
| Year 1 By June 2008, 25% of AUSD teachers will attend professional development, and will be proficient in the use of technology (such as Measures and / or Electronic Gradebooks, spreadsheets) to analyze student assessment data and make data-driven decisions to meet individual student academic needs and target student intervention needs. |  |  |  |
| Year 2 By June 2009, 50% of AUSD teachers will attend professional development, and will be proficient in the use of technology (such as Measures and / or Electronic Gradebooks, spreadsheets) to analyze student assessment data and make data-driven decisions to meet individual student academic needs and target student intervention needs. |  |  |  |
| Year 3 By June 2010, 75% of AUSD teachers will attend professional development, and will be proficient in the use of technology (such as Measures and / or Electronic Gradebooks, spreadsheets) to analyze student assessment data and make data-driven decisions to meet individual student academic needs and target student intervention needs. |  |  |  |
| Implementation Activities | Person(s) Responsible | Start | Completion |
| ## Annually in the fall, schedule and promote district sponsored technology workshops for administrators and for teachers during the school year on all SASIxp components. | 2 | 2007 | 2010 |
| Annually in the fall, schedule and promote district sponsored technology workshops for k-6 administrators and teachers during the school year on the district’s web-based student reporting system and Students at Risk procedures. | 2 | 2008 | 2010 |
| Annually in the fall, schedule and promote district sponsored technology workshops for k-6 administrators and teachers on the use of data analysis technology (such as Measures and / or class electronic grade books / spreadsheets) | 2 | 2009 | 2010 |
| Annually, provide systematic professional development and collaboration time for site administration and teachers to analyze student achievement data, align standards-based instruction, learn and share best practices in instruction and intervention, including the use of technology and develop quarterly assessments horizontally and vertically through grade levels in the district. | 1,2,5 | 2008 | 2010 |
| K -5 Assessment liaisons will continue to increase their skills in using Measures for assessing student data. | 2 | 2007 | 2010 |
| K- 12 Literacy and Math coaches will continue to increase their skills in the use of Measures. | 7 | 2007 | 2010 |
| District trainers will provide K -12 teachers just-in-time training in the use of Measures database. | 2 | 2007 | 2010 |
| 4 -12 Teachers will receive training to deliver online formative assessments. | 2 | 2007 | 2010 |
| 6-8 ELA and math teachers will receive training on the use of Quizdom for immediate feedback and formative assessments. | 2,7 | 2007 | 2010 |
| Teachers will receive training on district gradebook programs. | 2,7 | 2008 | 2010 |
| Teachers will be trained on the implementation of the selected online report card. | 2,7 | 2008 | 2010 |

| Goal 3 AUSD site administrators and teachers will become proficient in the use of technology to improve two-way communication between home and school. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Objective 3 By June 2010 75% of AUSD site administrators and teachers will become proficient with the district selected web –based communications package and technology for the development of newsletter and flyers and other home school communications. |  |  |  |  |
| Year 1 Benchmark By June 2008, 50% of AUSD site administrators and teachers will become proficient technology for the development of newsletter and flyers and other technology –based home school communications. |  |  |  |  |
| Year 2 Benchmark By June 2009, 50% of AUSD site administrators and teachers will become proficient with the district selected web –based communications package. |  |  |  |  |
| Year 3 Benchmark By June 2010, 75% of AUSD site administrators and teachers will become proficient with the district selected web –based communications package and technology for the development of newsletter and flyers and other home school communications. |  |  |  |  |
| Implementation Activities | Person(s) Responsible |  | Start | Completion |
| Teachers and administrators will receive training on Word and Desktop publishing tools to improve communication between home school and community. |  | 3,6,7 | 2008 | 2010 |
| Teachers and administrators will receive training on Microsoft Outlook Exchange email system. |  | 3,7 | 2007 | 2010 |
| Teachers and administrators will receive training on the use of the district selected web-based communication package. |  | 3,7 | 2008 | 2010 |
| Teachers and administrators will receive training on MS Front Page, Dreamweaver and SchoolCenter web publishing software. |  | 3,7 | 2007 | 2010 |

| Evaluation Instruments | Schedule for Collection | Person(s) Responsible |
| --- | --- | --- |
| Sign In Sheets | As workshops occur | 7 |
| EdTechProfile | Annually | 3,7 |
| Workshop Evaluations | As workshops occurs | 7 |
| Milestones for Improving Learning in Education Rubric from 21st Century Learning | Annual | 7 |
| Professional development calendars | Annual | 3,7 |
| 1. Principals 2.District Assessment Coordinator 3.Director of Technology 4.Site Technology Coordinators 5.Teachers 6.Director of Curriculum and Instruction 7.Technology TOSA 8.Media Specialists |  |  |

4d. Monitoring

AUSD curriculum, data and technology administrators, school site administrators, and the teacher on specioal assighnment will  track the development and implementation of all professional activities and accomplishments quarterly. Modifications to the district activities will be made as needed to insure the implementation of the professional development goals and benchmarks.  The Teacher on Special Assignment will monitor a significent portion of the professional development activities and make routine reports to Cabinet on the activities and results of the staff development.

Additional monitoring activities will include:

Classroom observations by

Principal

TOSA

Peer review / coaching

Analysis of skills training / testing – EdTech profile

5. INFRASTRUCTURE, HARDWARE, TECHNICAL SUPPORT AND SOFTWARE COMPONENT

5. b.	Summary of current AUSD technology hardware, electronic learning resources, networking and telecommunication infrastructure, that will support our tech plan objectives.

The hardware, Internet access, electronic resources and technical support that already exist in the district are described in Exhibit A. Additional details are provided below:

Single Computer Standard:  Alameda has moved to a Microsoft Windows based computer standard for both administrative and instructional applications.  Additionally, the Alameda Unified School District has standardized on the Microsoft Office Suite of personal productivity  Software.  Internet access is supported on both Internet Explorer  and Mozilla / Firefox web browsers.   Migration of all District server and client platforms to Microsoft products was completed in 2005.

Computer Inventory.

Alameda has a current inventory of 2453 computers, of which approximately 1,700 (69%) will meet the performance specifications established by this technology plan.

| School | Students |  | older than | I-Net | new | total | M/M |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | computers | 4 years | computers | comp |  | computers |
| Bay Farm | 558 | 114 | 48 | 114 |  | 114 | 66 |
| Earhart | 546 | 105 | 15 | 85 |  | 105 | 90 |
| Edison | 372 | 116 | 75 | 85 |  | 116 | 41 |
| Franklin | 286 | 66 | 0 | 38 | 32 | 98 | 98 |
| Haight | 438 | 120 | 106 | 102 |  | 120 | 14 |
| Lum | 508 | 129 | 98 | 129 | 34 | 163 | 65 |
| Otis | 386 | 62 | 51 | 58 |  | 62 | 11 |
| Paden | 374 | 92 | 56 | 46 | 25 | 117 | 61 |
| Ruby Bridges | 499 | 199 |  |  |  | 199 | 199 |
| Washington | 330 | 55 | 0 | 55 |  | 55 | 55 |
| Chipman MS | 604 | 101 | 0 | 101 |  | 101 | 101 |
| Lincoln MS | 944 | 90 | 0 | 90 |  | 90 | 90 |
| Wood MS | 719 | 85 | 41 | 85 |  | 85 | 44 |
| Alameda High | 1914 | 625 | 225 | 625 |  | 625 | 400 |
| Encinal High | 1189 | 220 | 0 | 160 |  | 220 | 220 |
| Island High (con) | 192 | 41 | 31 | 29 | 8 | 49 | 18 |
|  |  |  |  |  |  | 0 | 0 |
| ASTI | 84 | 40 | 0 | 40 | 34 | 74 | 74 |
| ACLC | 206 | 60 | 0 | 60 |  | 60 | 60 |
| District level | 10149 |  |  |  |  | 2453 | 1707 |

Computer Use

Each classroom has access to at least one computer workstation and printer at the current district standard ( Pentium 4 ).  Additionally each site has at least one current level lab and current level Media Center / Library.  All computers are networked via Cat-5 or Cat-6 cable, managed switches and each site’s has a minimum ( 100 meg ) high speed backbone fiber network connecting all school buildings.  As network equipment is being upgraded some sites and segments of the network are operating at 1gigabit per second.   Each workstation is able to access, retrieve, store, manipulate, organize, display, present and transmit data between the classroom, the school’s media center, and remote databases.  The classroom computers are connected to the School Library / Media Center’s electronic resources through the school wide LAN.  Approximately 69% of the districts computers ( 1700+ )  have sufficient processor speed, Memory, and disk space to support the applications software and  multi-tasking activities that are required by the existing curriculum, and future adoptions (e.g. concurrent use of word processing,  graphics, electronic mail, desktop publishing, multimedia, Internet access, etc.).

Each Teacher (classroom, computer lab, media, resource, itinerant, special education, counselor, etc.) has access to a desktop computer workstation.  Where appropriate, an itinerant teacher may be provided access to a laptop computer or a common computer / printer located in a work room, library or staff lounges.  These computers are used to  prepare lesson plans,  conduct Internet research for the lesson plans, acquire, store, and process data,  deliver technology rich instruction, and communicate with students, teachers, administrators, and parents.  All computers use the same operating systems and user applications software.  (See Exhibit B for Computer Specifications.  This specification is the minimum acceptable requirement for all Alameda educational applications.).

Currently, 21 instructional application servers and approximately 25 other administrative servers are in operation throughout the District.  All of the servers represent current technology and the newest version of network operating systems ( Windows Server 2003 )

Current Technical Support

Alameda Unified currently utilizes a site based support system of teachers and administrators referred to as the Site Technology Coordinator.  The site technology coordinators assume a significant responsibility for the site level technology support, and will off load the district level staff for basic computer / network support, maintenance and repair.  Additionally there is one network administrator, one district wide technician, one systems ( server ) analyst and one data base administrator, plus the department administrator to support the sites and computers.

Typical School LAN

A minimum of 2 data drops, 1 voice drop, and 1 CATV drops exist  to all classrooms. The minimum bandwidth speed is 100 Mbps.

Single person offices have at least one data drop.  Offices where several or many people are expected to work have a number of drops based on number of users.  Rooms other than classrooms and offices (e.g. staff rooms, conference rooms, theater stage areas, etc.) have at least one drop per room or area.  A minimum of one telephone drop is available for each room, plus an additional drop for fax machines where required.  A video co-axial drop is available in each classroom, auditorium, gymnasium, and conference room.

All classrooms offices and support locations within a school site are connected to each other and the school’s School Library/Media Center by means of a school-wide LAN.  The school-wide LAN uses Category 5 cabling within the building and fiber optic cabling between buildings.  The LAN is capable of delivering or receiving information at the rate of 100 Mbps minimum.  Each school LAN is connected to the Internet and the district’s Metropolitan Area Network (MAN) via a one gigabit fiber ring.

District Technology Training Lab.

Alameda Unified has a district-wide training lab with 28 computer workstations to train teachers, administrators and support staff on a variety of technology-based skills.  This facility is available to provide summer or inter-session training institutes, as well as training during school hours when the school facilities are not available for training.

5. a.	Summary of future technology hardware, electronic learning resources, networking and telecommunication infrastructure, that will be required to support our tech plan, staff development and curricular objectives.

The Alameda Unified School District has always been considered a leader in educational technology.  Over the past 5+ years we have implemented a state-of-the-art fiber network and provided every teacher with a current level computer work station.  In addition, we have provided at least one current level computer lab at every school.  As such we believe we are ahead of the implementation process and will only need replacement and future growth considerations for technology purchases.  As part of the future growth, AUSD will purchase anything necessary to support the ICT framework.

Computer Workstation Standards

Currently, a PC based computer with a chip speed of 2.8 GHz and 1 Gb of RAM capable of running Microsoft Windows XP Professional operating system and Microsoft Office XP Professional application suite will meet the majority of the teaching requirements for word processing, spread sheets, graphics, networking, Internet access, and multi-media.  The minimum performance requirements will be established annually to match the highest appropriately powered computer with identified needs.  Alameda will remain “on the leading edge, but not on the bleeding edge.”

All future AUSD computers will maintain the use of the District’s standard suite of productivity software and multimedia software  ( See appendix B for the District applications suite ).  Additional applications will be added as necessary for specific class functions.

School Library/Media Center Standards

The Media Center will combine library services and audio/visual multimedia services to support the integration of technology into the instructional program.  Students have, and will continue to have, direct access to an automated catalog of resources, CD-ROMS, multimedia production, integrated application software, and Internet access.  The School Library/Media Center at each school site will have a minimum of 5 networked multimedia computer workstations.  These workstations will be available for use by the students and the teacher during, and outside of, the classroom instructional period, and will have network access to all District resources as well as the Internet.

Laboratory Standards

Each Elementary School ( K-5 / K-6 ) will have access to a minimum of one (1) computer lab with a minimum of 30  networked computer workstations plus one teacher workstation.   The computer labs will be used (where appropriate) to accommodate large group research projects, provide large group instruction in computer hardware and software skills, and as a resource room to students during non-instructional periods.  The number of labs will be increased, to accommodate schools with larger enrolments.

Each Middle School (6-8 ) will have access to a minimum of one (1) computer lab per 500 students; each with 33 networked computer workstations plus one teacher workstation.  The computer labs will be used for large group research projects, large group instruction for hardware and software skills, and as a resource room for students during non-instructional periods.  Each computer station will have similar access to the School Library/Media Center electronic resources and remote resources through the network, and will have the same performance capability as the classroom computers.

Each High School will have access to a minimum of one (1) computer lab per 500 students with 35 networked computer workstations plus one teacher workstation.  As appropriate, the computer lab will be used for large group research projects, large group instruction for computer hardware and software skills, and as a resource room for students during non-instructional hours.  The number of labs or computers may be increased to accommodate larger enrollments   Additional networked computer workstations may be provided for specialized instructional areas, such as Business, Journalism, Science, Industrial Arts, Tutorial Centers, Visual Arts, etc. Each computer station will have the same performance capability as the classroom computers, and will have similar access to the School Library/Media Center electronic resources and remote resources through the network.

Computer Priorities.

The computer inventory will be updated at all schools each year to (1) identify the number of computers which meet the computer workstation specifications, (2) identify the additional computers that are needed, and (3) establish a priority sequence for computer procurements by site.  All of the administrative computers will be replaced on a three year cycle with 33% replaced each year.  Computers with functional life still available will be allocated to K-5 primary grades as needed.  The instructional computers will be replaced at the rate of 25%  per year over a 4-year period.  School Library / Media Centers / Labs will be replaced on a four year cycle with 50% of each lab at 50% of the total labs replaced each year ( it will take two years to replace all computers in a lab rather that 4 years, labs would still be on a 4 year cycle )

Internet and Multi-Media Priorities.

Each classroom, lab, media center and multi purpose room will have access to the appropriate multimedia technology that supports digital content, streaming media and visual demonstrations such as United Streaming, Brain Pop or on-line virtual labs and field trips.  This may include large format video displays, LCD projectors, wide screen televisions and DVD players.  Classrooms and sites will be upgraded by grade level as new curriculum adoptions are selected and implemented.

Phased Server Procurements.

Currently 21 instructional application servers and approximately 25 other administrative servers are in operation throughout the District.  The District will replace all servers on a five year cycle with approximately 20% of the capacity replaced every year.

Computer Technical Support

Alameda Unified currently utilizes a site based support system of teachers and administrators referred to as the Site Technology Coordinator.  The site technology coordinators assume a significant responsibility for the site level technology support, and off load the district level staff for basic computer maintenance and repair.  The coordinator’s responsibilities include the (1) training of site staff for basic instructional proficiency in the use of technology, (2) technology curriculum integration support at the classroom / grade level, (4) management/coordination of site web pages, (5) installation, troubleshooting and minor maintenance of site specific hardware, (6) installation and maintenance of virus protection and security software, (7) introduction of new software programs, (9) prioritization and call in for requests for service from the district level.  The site level coordinator will call upon the district level staff for computer maintenance and repairs that exceeds the capacity or expertise of the site level coordinator.

In addition to the site based support, the District will staff the Technology Services Department at a level comparable with similar districts as recommended in the FCMAT report of 2006.  This will provide a reliable level of support to all of the school sites.

The current technology staffing level is five (5) fte. The proposed Technology Services staffing plan is listed below by year and estimated number of district wide computers.

Proposed Technology Support, Staffing Plan

Plan year	1	   2	       3

| School Year | 07-08 | 08-09 | 09-10 |
| --- | --- | --- | --- |
| 1. Computers on Hand | 2,250 | 2,500 | 2,750 |
| - District Staffing Director of IT Help Desk Analyst Network Manager Network Administrator Systems Analyst Database Administrator Technicians Teacher on Special Assignment | 1 - - 1 1 1 2 1 | 1 - - 1 1 1 3 1 | 1 1 1 1 1 1 3 1 |
| 3. Total Proposed FTE | 7 | 8 | 10 |

5. c & d Benchmarks, timelines, and monitoring process for new hardware, infrastructure, and software acquisitions.

Goal 1 - District Goal for Hardware and Software

Goal 1: All AUSD students will have access to up-to-date computers and appropriate software to support achievement of the district’s academic standards in the classroom, district curricular goals, and ultimately for lifelong learning and success in our Digital society.

Specific Measurable Objective by June 30, 2010

Objective: 1a By June 30, 2010 our average student to computer ratio will be 4.0 to 1 or better ( by site ) (*based on CDE definition of up-to-date multimedia computer as - four year old or newer with multimedia capabilities). Annual Benchmarks and Timeline: Year 1: 6 students to 1 computer by June 2008 Year 2: 5 students to 1 computer by June 2009 Year 3: 4 students to 1 computer by June 2010. Objective: 1b By June 30, 2010, all 18 schools in the district will have access to new and / or upgraded district approved multimedia / AV technology to support new Math, History/Social Science and Science curriculum based learning and intervention software and/or internet subscriptions. (AUSD is in the process of new adoptions in most curricular areas ) Annual Benchmarks and Timeline: Year 1: 40% of classrooms by June 2008 Year 2: 60% of schools by December 2008. Year 2: 80% of classrooms by June 2009. Year 3: 100% of classrooms by June 2010.

Monitoring and Evaluation Instrument(s) & Data

Instrument: Annual CBEDS: Data: average student to computer ratio by school and district wide Instrument: Annual California School Technology Survey: Data: average student to computer ratio by school. Instrument: Annual district technology software survey Data: % of schools with access to approved curriculum based software Monitoring and Evaluation Process: The AUSD Technology Services Director, school site administrators, and site technology coordinators will track the development and implementation of all appropriate access activities, inventories and accomplishments periodically and report progress at bi-annual district/ site admin meetings. Modifications to our district activities will be made as needed in order to insure that we meet or exceed this measurable objective. AUSD Technology Services Director, school site admins., and school site tech coordinators will analyze end of school year results annually in June.

5. c & d Benchmarks, timelines, and monitoring process for new hardware, infrastructure, and software acquisitions.

Goal 2 - District Goal for Infrastructure

Goal 2: AUSD will continue to improve and maintain the infrastructure at district schools as needed.

Specific Measurable Objective by June 30, 2010

Objective: 2a Increase the number of local servers at the sites to meet site based storage requirements ( May include servers with internal hard drives or USB attached drives ) Annual Benchmarks and Timeline: Year 1: complete 4 schools by June 2008 Year 2: complete 3 more schools by June 2009. Year 3: complete 3 more schools by June 2010. Objective: 2b By June 2010, re engineer district network to provide reliable communications with redundancy and faster Internet connection Annual Benchmarks and Timeline: Year 1: by June 2008. Split the District’s one large ring ( unidirectional fiber ) into two smaller rings Year 2: by June 2009. upgrade the Districts Internet connection from 10 meg to 25 meg ATM Year 3: by June 2010. Evaluate and select network provider ( existing network agreement will expire )

Monitoring and Evaluation Instrument(s) & Data

Instrument: District and school infrastructure installation and purchase records Data: date, type, and location of infrastructure purchase and installation Monitoring and Evaluation Process: The AUSD Technology Services Director, school site administrators, and site technology coordinators will track the development and implementation of all appropriate access activities, inventories and accomplishments periodically and report progress at bi-annual district/ site admin meetings. Modifications to our district activities will be made as needed in order to insure that we meet or exceed this measurable objective. AUSD Technology Services Director, school site admins., and school site tech coordinators will analyze end of school year results annually in June.

5. c & d Benchmarks, timelines, and monitoring process for new hardware, infrastructure, and software acquisitions.

Goal 3 - District Goal for Technical Support

Goal 3: All AUSD school sites will have access to timely district or site technical support to so teachers and students have access to technology needed to support standards in the classroom, district curricular goals, and ultimately for lifelong learning and success in our Digital society.

Specific Measurable Objective by June 30, 2010

Objective: 3a By June 2008, the district will have an standardized Information Technology Services (ITS) work order process and tracking system in place. Annual Benchmarks and Timeline: Year 1: 100% by June 2008. Year 2-3: Revise and maintain as needed Objective: 3b By June 2008, the district will have new / upgraded computer, software, network, and security standards in place for district supported technology.(i.e. Virus protection, DeepFreeze software, web content filtering software, Spam Blocking) Annual Benchmarks and Timeline: Year 1: 50% by June 2008. Year 2: 100% by June 2009 Objective: 3c By June 2010, the district will have adjusted the staffing levels to a ratio of one computer tech to 750 computers ( see staffing proposal in 5.a. ) Year 1: by June 2008. Increase Technology Services staff from 5 to 7 ( 2 computer techs ) Year 2: by June 2009. Increase Technology Services staff from 7 to 8 ( 3 computer techs ) Year 3: by June 2010. Increase Technology Services staff from 8 to 10 ( 3 computer techs )

Monitoring and Evaluation Instrument(s) & Data

Instrument: District Polices and Procedures handbook and/or web postings Data: Standardized work order process and security standards for computers and networks. Instrument: District job postings and personnel changes Data: hiring records / staff reports Monitoring and Evaluation Process: The AUSD Technology Services Director, school site administrators, and site technology coordinators will track the development and implementation of all appropriate access activities, inventories and accomplishments periodically and report progress at bi-annual district/ site admin meetings. Modifications to our district activities will be made as needed in order to insure that we meet or exceed this measurable objective. AUSD Technology Services Director, school site admins., and school site tech coordinators will analyze end of school year results annually in June.

# 6. Ed. Technology Funding & Budget

Economic conditions in California and the nation will continue to impact k-12 education budgets and grants through the duration of our tech plan. Therefore, our established and potential funding sources to implement our Educational Technology Plan may be impacted as well.

Technology funding and budget planning will take place on an ongoing basis guided by the goals and objectives of this plan.

In developing the budget for the District’s Ed Tech Plan, we took into consideration the District’s Strategic ( long range) plan and five-year curricular goals for our students and staff.

6a. List of established and potential funding sources

Established funding sources:

The District’s General Fund pays for:

- The salaries for the Technology Services staff,

- SASI implementation & growth of application of components,

- Tech help support,

- Internet Service Provider fees

- Other equipment/tools used by the Information Services department.

- School site budgets (title 1, PTA) also pay for some local site technical support,  computers & peripherals, and staff development.

EETT grants also pay for professional development based on the grants applications

A local bond measure and E-rate offsets pay for:

- Infrastructure upgrades

- Phone service

- District computers, printers and servers

- Extra technical help for special project deployment

- Multimedia and AV classroom equipment

- Staff development

CTAP provides in-kind coordinator time to assist with Technology Planning and implementation.  CTAP also offers after-school technology workshops (for a fee) and Summer Teaching and Learning Collaborative conference at the CSUC campus each summer (for a fee) that help us meet our technology plan objectives.

Regarding the continued need for up-to-date student and teacher computers (4 years old or newer) and for site technical help, these are the biggest budget challenges for technology in our district. District and Site budgets from various sources help pay for needed hardware.

Potential funding sources:

- EETT Formula grant

- EETT Competitive grant

- Microsoft Voucher

- Title 1 and SIP monies

- Library improvement grants

- PTA and community donations

Budget Assumptions in formulating three year cost models:

- District-paid and site-paid tech support will continue at the same level.

- DAS/CPUC/CA Teleconnect Fund and the Federal E-rate program will continue throughout the duration of the Ed tech plan.

- EETT Formula grant funds will continue at approximately the same funding rate throughout the duration of the Ed tech plan.

- EETT Competitive grant continues to be available to grades 4-8 upon successful grant application approval.

- The District staff development time will be at the teacher / principal / district’s discretion throughout the duration of the plan.

- There will not be any state or district budget freezes for the duration of our Tech Plan.

- School site budgets and Title 1 funds will fund some of the site specific hardware, software, professional development, and tech support outlined in the plan.

- Microsoft Voucher program will offset one-time costs at eligible schools

Given the uncertainty of our Ed tech sources of funding, we have established the following priorities list to guide allocation:

- District-wide technical support

- Updated student and teacher computers

- Infrastructure upgrades

- Staff development for standards-based curricular software.

- Staff development for administrators – web searching, basics file management & how to work with attachments, where to find educational resources

6b. Estimate of AUSD Staffing Costs for Three Year Ed Tech Plan

| Projected Ed Tech plan staffing |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 07-08 | 08-09 | 09-10 |
| Director |  |  |  |  |  | $130,000 | $130,000 | $130,000 |
| Network Administrator |  |  |  | $85,000 |  |  | $85,000 | $90,000 |
| Systems Analyst |  |  |  |  | $80,000 |  | $80,000 | $85,000 |
| Database Administrator |  |  |  | $75,000 |  |  | $75,000 | $80,000 |
| Technicians |  |  |  |  | $140,000 |  | $210,000 | $210,000 |
| TOSA |  |  |  |  |  | $90,000 | $90,000 | $95,000 |
| Help Desk |  |  |  |  |  |  |  | $60,000 |
| Net Mgr |  |  |  |  |  |  |  | $100,000 |
| Total Staff members |  |  |  |  | 7 |  | 8 | 10 |
|  |  |  |  |  |  | $600,000 | $670,000 | $850,000 |
|  |  |  |  |  |  |  |  | $2,120,000 |

6b. Estimate of Total AUSD Tech Plan Implementation Costs for Three Year Ed Tech Plan  ( including examples of items to be purchased )

| Tech Plan year | 07-08 | 08-09 | 09-10 |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Total by type | Funding Source |
| Staffing | $600,000 | $670,000 | $850,000 | $2,120,000 | General fund, Categorical funds |
| - Help desk - Tech support - Other support staff |  |  |  |  |  |
| Computers / printers | $300,000 | $509,000 | $340,000 | $1,149,000 | Grants, Bonds, Site based |
| Multimedia A/V | $31,000 | $39,000 | $23,000 | $93,000 | Grants, Bonds, Site based |
| - TVs - LCD projectors - Document cameras |  |  |  |  |  |
| Software | $5,000 | $10,000 | $15,000 | $30,000 | Microsoft Voucher, |
| - MS Office - Adobe Suite - SME - Math Tech |  |  |  |  |  |
| Infrastructure | $19,500 | $19,500 | $19,500 | $58,500 | Bond funding |
| - Switches - Routers |  |  |  |  |  |
| Professional Development | $35,000 | $40,000 | $45,000 | $120,000 | Microsoft Voucher, General fund, Categorical funds, Site funds |
| - Tech leaders - Peer trainers - Vendor provided - Seminars and conferences |  |  |  |  |  |
| Total by year | $990,500 | $1,287,500 | $1,292,500 |  |  |
|  |  |  | Total | 3,570,500 |  |

6c. Level of Ongoing District Technical Support

There is continued need for technical support at the site level.  Each site has a technology support person or Media Center person that provides initial technology response.  The District is committed to staffing the Technology Services Department to the levels recommended in the 2006 FCMAT report.

Proposed Technology Support, Staffing Plan

Plan year	1	   2	       3

| School Year | 07-08 | 08-09 | 09-10 |
| --- | --- | --- | --- |
| 1. Computers on Hand | 2,250 | 2,500 | 2,750 |
| - District Staffing Director of IT Help Desk Analyst Network Manager Network Administrator Systems Analyst Database Administrator Technicians Teacher on Special Assignment ( not a FCMAT requirement ) | 1 - - 1 1 1 2 1 7 fte | 1 - - 1 1 1 3 1 8 fte | 1 1 1 1 1 1 3 1 10 fte |

6d. District’s Replacement Policy for Obsolete Equipment

AUSD Replacement guideline for obsolete equipment is every four years. Our computer replacement budget is approx $210,000 per year, with projected funding sources of district and site general funds, site Title I funds, grants, and Bond funding.  Principals work with the District and School Site Councils to review tech inventories for the school and modify budgets where necessary.

6e. District’s Budget and Funding Monitoring Process

AUSD is committed to a dependable and sustainable technology plan that ensures funding for reliable infrastructure, hardware, technical support, professional development, and software for all district sites.

The AUSD Director of Technology Services along with Assistant Superintendent of Curriculum, and the Chief Financial Officer, have the primary responsibility and access to appropriate budgets to meet goals and objectives specified in this plan.  District technology budgets and funding monitoring is the responsibility of the Director of Technology Services who takes budget recommendations and revision requests to Cabinet-level meetings and the School Board as needed. The Director of Technology Services will make fiscal reports to the School Board, and Cabinet yearly in July, based on expected requirements for the upcomming school year, and again in February as a mid term correction.   Additionally, the Director of Technology Services will make quarterly reports to the Technology Steering Committee and the Bond Oversight committee regarding current and future expenditures.   Routine district budget analyses and funding opportunities are tracked to ensure optimal leveraging of funds. Site technology budgets are the domain of site principals and school site councils. Technology funding and budget planning will take place on an ongoing basis guided by the goals and objectives of this plan.

Given the annual uncertainty of federal, state, and private Ed. Tech sources of funding, the district Technology Advisory Committee will annually recommend funding priorities to the AUSD Director of Technology Services to guide technology budget allocations.

District technology support and site-based technology staff provide the AUSD Director of Technology Services ongoing data on technology replacement, upgrades, maintenance, and technical support needs including the annual online California School Technology Survey data provided by all sites in the district, as well as CBEDS data collected each October.

7. Monitoring & Evaluation of Technology Plan

7. a. Description of how technology’s impact on student learning and attainment of the district’s curricular goals, as well as classroom and school management, will be evaluated.

The Alameda Unified School District is committed to achieving high standards in curriculum and student learning results, and sees the Educational Technology Plan as supporting the curricular goals and student achievement goals of the District.   The Educational Service Division, which encompasses Technology Services, Curriculum and Instruction, and Assessment, will coordinate the evaluation of the Technology plan as it impacts student learning and curricular goals.

To evaluate the impact of the technology plan on student learning, a variety of normed and criterion based assessments,  including the California Standards Test (CST), California High School Exit Exam, and a variety of AUSD assessments more closely aligned to the District’s curricular goals, will be used.

Included among our curricular goals are student use of and competence with technology. This will be evaluated by student and teacher surveys (CA School Technology Survey and Ed Tech Profile) and examples of student work. Increases in teacher skills that allow them to better integrate technology will also be assessed by feedback forms at the end of staff development sessions.

The degree to which the technology is integrated into the learning environment and supports classroom and school management will be measured using indicators such as student-computer ratios, student and teacher surveys (CA School Technology Survey and EdTech Profile), and classroom observations of student engagement with technology resources

7. b. Schedule for evaluating the effect of plan implementation.

The following chart specifies who is responsible for the monitoring and evaluation activities and when that evaluation will occur.

| Job Title(s) of Responsible Individual(s) | Responsibilities | Timeline |
| --- | --- | --- |
| AUSD Coordinator of Assessment | Provide analysis of student achievement gains and areas of need based on STAR assessments | Yearly in Sept. |
| AUSD Coordinator of Assessment | Provide analysis of pass rates s from CAHSEE administrations | Yearly in May |
| AUSD Coordinator of Assessment | Provide analysis of student progress based on AUSD formative assessments | Quarterly |
| AUSD Director of Technology and Teacher on Special Assignment | Provide analysis of growth in technology use, skills, and needs based on Ed Tech Profile teacher and student surveys | Yearly- September |
| Principals, AUSD Director of Technology, and Teacher on Special Assignment | Provide analysis of technology availability in classrooms and schools based on Ed Tech Site survey | Yearly in September |
| Principals, Site technical coordinators, Director of Technology | Provide classroom/ school technology integration data based on observations | Ongoing |
| Director of Technology, AUSD Coordinator of Assessment, Director of Curriculum | Provide analysis of data from staff development sessions | Ongoing |
| AUSD Technology Services Director AUSD Teacher on Special Assignment Core Technology Team | Use collected data to monitor and evaluate progress toward benchmarks and the timeline and to plan and make modifications. | Oct., Feb., June |

7. c. Description of how the information obtained through the monitoring and evaluation will be used.

Each identified objective in our Technology Plan will be reviewed and evaluated quarterly by the Alameda Unified School District Technology Advisory Committee.  Committee membership includes: the Technology Services Director, the Teacher on Special Assignment, the Assistant Superintendent of Education Services and various site based staff members and parents.  This committee will have the overarching responsibility for ensuring that our goals and objectives are monitored, adjusted as necessary, and accomplished.

Student achievement and curricular goals will be monitored by the Educational Services Division based on the data outlined in 7b.  As is in place throughout the district, Ed Services uses a continuous improvement model for using data to improve implementation of programs/plans and to improve instructional outcomes as shown by data. This process will be applied to the District Technology Plan as it is to all District planning processes.

The following chart specifies who is responsible for necessary adjustments and possible corrections to the plan as well as identifying reporting structure to stakeholders and oversight committees

| Job Title(s) of Responsible Individual(s) | Responsibilities | Outcomes | Monthly FTE Time Estimate |
| --- | --- | --- | --- |
| Technology Services Director, Assistant Superintendent of Curriculum, Teacher on Special Assignment | Provide overall Tech Plan management and coordination | Reports to Superintendent, school board and stake holders | 5% each |
| Technology Services Director CTAP Tech Coordinator | Assess, plan implementation and evaluate technology staff development aligned to curriculum. | Report to Assistant Superintendent of Curriculum, adjust as necessary, align staff development with curricular needs | 5% each |
| Technology Services Director Teacher on Special Assignment | Standardize, develop, manage, monitor, and revise as necessary network, hardware, infrastructure, software, and technical support specifications, policies, and procedures. | Reports to Superintendent, school board and stake holders use of, and or need, for additional technology resources | 5% |
| Testing and Assement Director Site Technology Coaches | Collect and analyze data regarding K-5, 6-8, and high school students’ computer skills. | Report to Technology Services Director, Assistant Superintendent of Curriculum, Teacher on Special Assignment, adjust as necessary | 2% |
| Technology Services Director Teacher on Special Assignment | Collect staff development data on technology proficiencies | Report to Assistant Superintendent of Curriculum Provide additional staff development ( Nets / TechSets, Adult Ed,…) | 5% |
| Technology Services Director CTAP Tech Coordinator consultant Teacher on Special Assignment | Use collected data to monitor and evaluate progress toward benchmarks and the timeline and to plan and make modifications. | Reports to Superintendent, school board and stake holders | 5% |

8.0	ADULT LITERACY PROVIDERS

Within the Educational Services Office, the Director of Secondary Ed/ROP and the Principal of the Adult School have collaborated to provide adults access to technology through several existing programs. The Regional Occupational Program (ROP) offers a variety of computer training opportunities such as Computer In Business, Desktop Publishing, A+/Web Design, and Cisco Network Cabling Technology. These free classes are open to all residents of Alameda, who are at least 16 years old. Classes are offered mornings and afternoons at high school campuses. These training programs provide citizens within the community with career guidance, hands-on training, and job placement assistance to help ensure success.

Through the Adult School, Adult Computer Literacy Courses are open to all adults in our community. Eligibility requirements are that the participants are eighteen years old. Courses offered are Introduction to Computers, Windows Operating System, Microsoft Suite, Computer Graphics/Photo Editing,  Upgrading to Windows XP, Introduction to the Internet, Creating a Web Page and PC Maintenance Technician A+  Certification. These are lecture style courses that also involve a specific amount of hands-on lab time.

Also managed by the Educational Services Office and coordinated by the Director of Special Programs, another successful program implemented by the district is the Community Based English Tutoring program through Woodstock Elementary School. Woodstock has computer labs that participants can access during the day or after school hours. This program uses SuccessMaker to introduce parents to English acquisition utilizing technology. Parents learn computer skills and information literacy as a byproduct of acquiring and or improving their English.

The District, through the auspices of the Educational Services Office, will continue to explore the possibilities of creating opportunities, which will allow parents computer access and training on basic computer literacy skills by continuing to work closely with College of Alameda, the school libraries, the public libraries, and the schools involved community-based programs to assess and to determine the needs of the adults in the community.

# Criteria 9: Effective, Research-Based Methods and Strategies

9a Description of how education technology strategies and proven methods for student learning, teaching, and technology management are based on relevant research and effective practices:

9b. Description of thorough and thoughtful examination of externally or locally developed education technology models and strategies.

Our technology vision flows from the district Strategic Plan and Graduate Profile.  The

methodology is guided by six recommendations made by the CEO Forum in the School Technology and Readiness Report. Those six recommendations are:

1. Focus education technology investment on specific educational objectives.

2. Make the development of 21st Century skills a key educational goal.

3. Align student assessment with educational objectives and include 21st century skills.

4. Adopt continuous improvement strategies to measure progress and adjust accordingly.

5. Increase investment in research and development and dissemination.

6. Ensure equitable access to technology for all students.”(CEO Forum School Technology and Readiness Report, June 2001 page 3)

Our educational objectives have measurable goals linked to improved student achievement. We have incorporated the 21st Century literacy skills including inventive thinking skills, communication, interpersonal skills and productivity skills into technology standards and benchmarks that align to state content standards. Strong programs in Information Literacy based in the Library Media Centers are either in place at our sites or in development.  Library Media Teachers in the high schools collaborate with English and 9th grade science teachers to deliver these programs.

We believe that the teacher’s ability to assess student learning is key to improving student

achievement.  We believe in data-driven decision making.  Our technology plan includes goals to continue implementing the use of electronic standards-based assessment and reporting tools by every teacher. Our teachers receive ongoing training in the use of the district adopted Measures Applied Plus software.  In a further effort to align student assessment with educational objectives we are developing district wide common assessments that can be administered online, using the Measures Aligned Software.  Many such assessments have already been created including online finals in chemistry and physics. The detailed reports provided by Measures Applied for STAR and other standardized testing, and by Measures Aligned for district and site made tests, provide the basis for data driven decision making.  Further ongoing training provided by the district assessment office helps develop teacher and administrator skill in such decision making.  We are also developing and implementing student assessment instruments for district technology standards and benchmarks.

Our goals correlate to continuous improvement strategies with evaluation instruments for formative assessment, specifying data to be collected and identifying the persons responsible. Progress towards our meeting goals is constantly and regularly reviewed with provision for making necessary modifications.

Some of the goals and objectives in the plan have an emphasis on research and development, such as goals for developing bold, colorful presentations to assist visual learners master abstract concepts and difficult skills.  The benefits of use of this strategy are strikingly supported in Zywno, M and Waalen, J (2002) The Effect of Individual Learning Styles on Student Outcomes in Technology-enabled Education, Global J of Engng. Educ, Vol 6, no. 1.

We further agree that “Technology can provide the means for students with special needs to communicate via email and use the Internet for research, and can also help teachers accommodate students’ varying learning styles.” Silverstein, G., Frechtling, I., & Miyoaka, A. (2000). Evaluation of the use of technology in Illinois public schools: Final report (prepared for Research Division, Illinois State Board of Education). Rockville, MD: Westat.

“Gifted students can work at their own pace and explore subjects in more depth than the basic curriculum. Technology can also analyze and provide immediate feedback on performance, and can suggest modifications in instruction where necessary to improve student achievement.”  CEO Forum on Education and Technology. (2001

Our confidence that technology integration boosts student achievement also relies in part on research conducted by The Idaho Council for Technology in Learning published in 1999 based on the effect of the technology initiative in Idaho. Researchers examined the test score gains, technology usage patterns, and technology literacy along with five other elements of the initiative. The sample consisted of over 35,000 8th and 11th grade students, and the researchers concluded “There is a positive relationship between academic performance in core studies, language, math, and reading and the integration of technology in Idaho’s K- 12 schools (p. vii They also concluded that the gains were greater for 8th graders than for 11th graders and that the differences between the academic gains of Idaho students with high exposure to computers over a four year period and the academics gains of those students who had little interaction with computers over that same time were practical and educationally meaningful. The technology factors that were the strongest predictors of achievement gains were the ability to choose the appropriate software tool, the amount of computer use at school, exposure to Internet and email use, and the amount of computer use at home.

Idaho Council for Technology in Learning (1999). The Idaho technology initiative: An accountability report to the Idaho Legislature on the effects of monies spent through the Idaho Council for Technology in Learning. The State Division of Vocational Education, The State Department of Education, Bureau of Technology Services.

In our district technology plan, professional development is a primary focus.  The district began participating in the very intensive “Intel Teach to the Future” program in 2000.  Five district teachers became Master Teachers in the program and they subsequently trained over 150 of our teachers, or nearly 1/4th the total.  These teachers received more than 40 hours of concentrated, hand-on training.  This gave our district a big boost both in the capability of teachers to use technology tools such as the Office Suite and in skills for integrating technology effectively into coherent classroom units and rubric-based grading.

Helping teachers to learn to integrate technology into curriculum is a critical factor in the successful implementation of technology in schools: Sivin-Kachala, J., & Bialo, E. (2000). 2000 research report on effectiveness of technology in schools (7th ed.). Washington, DC:  Software and Information Industry Association. “…when teachers are learning to integrate technology into their classroom, the most important staff-development features include opportunities to explore, reflect, collaborate with peers, work on authentic learning tasks, and engage in hands-on, active learning.” Schacter, J. (1999).

The constructivist bent of the Intel training aligns well with the research of  Becker, J.H., and Riel, M.M. (2000). Teacher professional engagement and constructivist-compatible computer use, Center for Research on Information Technology and Organizations. Retrieved September 23, 2002, online http://www.crito.uci.edu/tlc/findings/report_7/startpage.html

This report describes a number of aspects of the professional engagement of American teachers. It also examines relationships between professional engagement and teaching practice, including instruction involving computer use. In this context professional engagement involves collaboration of teachers within and across schools.  This matches up strongly with the emphasis on collaboration in our district Strategic Plan.  Teachers at all our sites have regular and substantial time set aside for collaboration, including collaboration on technology integration.

Using network folders on district and site servers, our teachers routinely share documents and presentations made with technology.  Literally hundreds of these electronic presentations are made available to students on the Web via school websites.  Many teachers post their assignments online and some post daily grades.

Professional engagement also includes conference presentations.  One teacher who was the LEA contact for the Intel program and the Project Director for the Digital High School Program at one high school made notable contributions in presentations made at CTAP Region 4 and had a role in catalyzing a successful online commercial math website, which initially was developed in conjunction with one of our high school math departments.

Teacher professional development has continued under the auspices of the Alameda Adult  School, which has created several popular courses.  Other teachers have taken online courses including those offered by CTAP Online.  CTAP Online matches up against the design elements for high quality professional development as outlined in the Designs for Learning. Designs for Learning was developed by the California Professional Development Reform Initiative, which was sponsored by the California Department of Education with support from the California Professional Development Consortia, the Center for the Future of Teaching and Learning, the California Staff Development Council, and the New Teacher Center. http://www.cde.ca.gov/pd/ps/te/designs4lrng.asp

Teacher participation in technology use received a huge boost in 2004 when the district, using Measure C funds, provided all teachers with new computers and Outlook based email accounts.  Shortly afterward the district moved all attendance taking online, using SASI CLASS XP, and shortly after that progress report, quarter, and semester grades were required to be posted on CLASS XP as well.  This familiarized technology late adopters with technology tools and encouraged nearly full participation by district teachers.

Our plan is influenced by the work of Marzano, R, Pickering, D., and Pollock, J. (2001). Classroom instruction that works: Research-based strategies for increasing student achievement. Virginia: Association for Supervision and Curriculum Development.

This book summarizes the research supporting a variety of instructional strategies with proven successes in improving student achievement. The research-based strategies include 1) identifying similarities and differences; 2) summarizing and note-taking; 3) reinforcing effort and providing recognition; 4) homework and practice; 5) nonlinguistic representations; 6) cooperative learning; 7) setting objectives and providing feedback; 8) generating and testing hypotheses; and 9) cues, questions, and advance organizers.

Technology helps us implement these strategies.  Student Internet research provides engaging ways to apply these strategies. Simulation software allows students to generate and test hypotheses quickly and efficiently. Using presentation software to organize information, coupled with using a printed copy of the presentation to assist in note-taking skills, helps students to better identify key concepts and summarize critical information.

Computer assisted instruction also plays a role in our Technology Plan.  Beginning in 2001 Pearson “Successmaker.” was introduced at nearly all of our sites.  This software helps customize instruction in Language Arts and Mathematics skills.

Analysis of 500 computer-based instruction studies concluded that computer-assisted instruction and drill and practice software can significantly improve students’ scores on standardized achievement tests. Kulik, J.A. & Kulik C.-L. C. (1987a) Computer-based instruction:  What 200 evaluations say.  Paper presented at the Annual Convention of the Association for educational Communications and Technology, Atlanta, GA. (ERIC Document Reproduction Service No. ED 285 521)

9c. Description of development and utilization of innovative strategies for using technology to deliver rigorous academic courses and curricula, including distance learning technologies.

The Alameda Unified School District utilizes streaming video, virtual labs, and limited distance learning opportunities.  We understand the current limitations of our distance learning and video programs and will be exploring additional opportunities as we adopt new curriculum at the middle and high school level over the next several years.

Our high schools have strong college prep and Advanced Placement Programs in science and math.  In Statistics and Physics courses technology plays an important role.  In both Physics(P), AP Physics and Chemistry the laboratory program is becoming increasingly technology based.  Most labs use Vernier Data Collection technology.  Students collect data with electronic sensors and analyze the data using Logger Pro and Excel software.  The courses are partially inquiry based.  Further development of Physics and Chemistry inquiry based instruction is proceeding under a grant from Toshiba America Foundation.  Numerous research articles support the use of data collection technology in science instruction:

Arnold, Steve, Pat Taylor and Jacqueline Spencer. "The Use of Calculator-Based Laboratory Equipment in Teaching Math, Chemistry, and Biology". Inquiry. 3 Fall 1998, 6-8.

Krajcik, Joseph S. and Layman, John W. "Microcomputer-Based Laboratories in the Science Classroom". University of Michigan and University of Maryland.
http://www.educ.sfu.ca/narstsite/publications/research/microcomputer.htm

Lapp, Douglas Ph.D. and Dr. Vivan F. Cyrus "Using Data Collection Devices to Enhance Student Understanding". Central Michigan University. 2000.
http://calcnet.cst.cmich.edu/faculty/lapp/MT2000.pdf
This same paper can be found in Mathematics Teacher. 93 September 2000. 504-509.

Stager, Gary S. "Empowering Young Mathematicians and Scientists Through Technology". Curriculum Administrator. October 1998.
http://www.stager.org/articles/Mathsciencecafeature.html

Redish, Edward F., Jeffery M. Saul, and Richard N. Steinberg. "On the Effectiveness of Active-Engagement Microcomputer-Based Laboratories." American Journal of Physics. Volume 65. 45 - 54 (1997)
http://www.physics.umd.edu/perg/papers/redish/mbl/mbl1.html

Redish, Edward F., Jeffery M. Saul, and Richard N. Steinberg. "On the Effectiveness of Active-Engagement Microcomputer-Based Laboratories: Part 2."
http://www.physics.umd.edu/perg/papers/redish/mbl/mbl2.html

Durick, Mary Ann. "The Study of Chemistry by Guided Inquiry Method Using Microcomputer-Based Laboratories." Journal of Chemical Education 78 (2001): 574-575.

Jones, Rebecca B. "Life before and after Computers in the General Chemistry Laboratory". Journal of Chemical Education. 77 August 2000. 1085-1087.

We have a goal to expand the use of data collection technology to other high school courses such as Biology, Physiology, Earth Science and Environment and to other sites in the district, especially middle schools.  This will provide equitable access to all AUSD students as recommended by item 6 of the CEO Report.

Appendix A

Computer

Performance Specifications

The Computer Workstation must possess adequate chip speed, random access memory, hard disk storage, video display and DVD player / writer for the tasks required of the machine.  The minimum specifications for Computer Workstation will be reviewed annually for modification.

| Feature | Computer |
| --- | --- |
| Cache Processor RAM Hard Drive DVD Video Card Network Card Operating System Monitor Software | 512 Kb Pentium D-945 3.4 Ghz 1 Gb 80 Gb SATA Drive 8X /DVD RW SATA 128 Mb 100/1000 Mbps Win XP Pro 17”, .26 dpi MS Office XP, Front Page, Hyperstudio, Encarta |

Appendix B

Computer Software Specifications

The Computer Workstation must possess adequate chip speed, random access memory, hard disk storage, video display and DVD player / writer for the tasks required of the machine.  The minimum specifications for Computer Workstation will be reviewed annually for modification.

| Feature |  |
| --- | --- |
| District Standard Software | Windows XP or 2003 MS Office XP, or 2003 MS Front Page, MS Access MS Visio MS Outlook Palm Quick Time IE, Mozilla, or Firefox Antivirus software ( currently negotiating for new software ) |

| Feature |  |
| --- | --- |
| District Specialty Software Actual installation varies by site, grade, and Ed programs | Kid Pix MathTech SuccessMaker AutoCAD United Streaming Renzulli Brainpop |