Alameda Unified School District

Educational Services

5-Year Arts Education Plan

| I. Focus Area: Teaching and Learning |  |  |
| --- | --- | --- |
| Goal #1: Ensure equitable access to VAPA Education for all students in all schools everyday |  |  |
| 1.1: Research & implement ways to make VAPA accessible to all students | Phase I (2007-2009) Suggested Strategies, actions, and activities: | Phase II (2009-2012) Suggested Strategies, actions, and activities |
|  | Reinstitute summer school offerings, i.e. make up failed courses, Current Life Issues, PE in order to allow students to take more courses in the arts during the school year | Train core teachers to integrate the arts in the classroom |
|  | Implement Computer-based art program at EHS & IHS (ROP) | Use the current PE/Music prep format as a way to procure quality visual art instruction at the elementary level |
|  | Expand school year classes into “extended school year program”; i.e. spring break, winter break, summer | Offer before/after school elementary art, music and dance free for those interested (collaborate with current ASES/21st Century after school grants) |
|  | Budget: Approximately $20,000: Ongoing Art & Music Block Grant | Staggered scheduling for teachers & students to create accessibility to the arts classes (performing arts teachers + a production = # of hours class meets) |
| 1.2: Research and implement schedule changes that provide greater accessibility to the arts | Make scheduling and staffing a priority providing for teachers in dance, music, theatre, visual arts, chorus, band, multimedia |  |
|  | Flexible student numbers for classes by subject and level |  |
|  | Initiate 0-7th period VAPA classes (secondary) |  |
|  | Review, refine and develop VAPA stipends to ensure equitable stipends for teachers |  |
|  | Budget: Approximately $52,000: Ongoing Art & Music Block Grant |  |
| I. Focus Area: Teaching and Learning |  |  |
| Goal #2: Develop and implement a comprehensive K-12 standards-based VAPA curriculum that is cohesive and inclusive |  |  |
|  | Phase I (2007-2009) Suggested Strategies, actions, and activities: | Phase II (2009-2012) Suggested Strategies, actions, and activities |
|  | Establish a committee to develop a standards-based VAPA curriculum | Implement resource sharing between programs |
|  | Implement the key standards in the arts at the elementary level delivered by classroom teachers | Provide Music in Kindergarten daily |
|  | Evaluate specialized elementary programs and revise as necessary (Media, PE, Music) | Share a credentialed art teacher for 1hr./week at elementary level. Hire one music teacher per school |
|  | Support field trips as a necessary component of VAPA curriculum | Ensure an appropriate teacher to student ratio in VAPA classes (Grades 1-3) 20:1 |
|  | Implement vertical K-12 arts program, ending in AP portfolio to ensure consistent and coherent programs are available at each school especially middle and high school | Have East and West end after school instrumental programs (band) |
|  | Research and evaluate how to share resources and maximize buying power among programs |  |
|  | Budget: Approximately $20,000 – Ongoing Art & Music Block Grant |  |
| I. Focus Area: Teaching and Learning |  |  |
| Goal #3: Ensure highly qualified VAPA professionals who are passionate about teaching and the arts |  |  |
|  | Phase I (2007-2009) Suggested Strategies, actions, and activities: | Phase II (2009-2012) Suggested Strategies, actions, and activities |
|  | Provide professional development for core teachers in arts on an Interdisciplinary (art, music, drama, history, science, math, etc.) approach so teachers at all levels (elementary, middle, high) teach all subjects through the arts. | Provide a choral position at middle schools and EHS, (1 period paid to travel) |
|  | Tap into County Arts Ed programs for staff development– i.e. Values Project-Art is Education - Define sub release time | Establish a connection with local colleges/universities to seek out “highly qualified” teachers |
|  | Hire elementary teachers with arts background - Survey arts expertise in AUSD | Hire dance teachers at secondary sites, as needed |
|  | Hire dedicated, appropriately credentialed visual and performing arts teachers at elementary schools. | Hire strings orchestra teacher for high schools. |
|  | Research and procure professional development in standards-based curriculum and instruction | Assemble a roving team of (specialized) teachers to teach all students. Music: choir, jazz, concert, orchestra, marching band. Teach to your strength/teach to your passion |
|  | Initiate cross grade level articulation through collaboration - Provide stipends to coordinate and support this at sites that don’t have it. | Utilize the art teacher at elementary schools as a resource for classroom teachers for curriculum integration. |
|  | Set up networking articulation, sharing opportunities within the district. |  |
|  | Budget: Approximately $20,000 – Ongoing Art & Music Block Grant |  |

| II. Focus Area: Communication for Motivating Change - Advocacy |  |  |
| --- | --- | --- |
| GOAL #4: Provide on-going communication about the power of arts learning |  |  |
|  | Phase I (2007-2009) Suggested Strategies, actions, and activities: | Phase II (2009-2012) Suggested Strategies, actions, and activities |
|  | Provide opportunities for showcasing student learning in the arts. Be our own advocates – Take the arts to the community - Concerts for feeder schools - Art shows - Art in the Park - Music in the Park - Commedia del Arte - Parades | Understand and communicate the importance of media and visual literacy |
|  | Organize AUSD Day of the Arts (i.e. open studios) | Implement advocacy/messaging campaign |
|  | Promote communication of arts based research and student achievement |  |
|  | Get speakers from “Art Is” program at County Office (tap into the program) |  |
|  | Create an advocacy slogan/message/sales pitch for community about the value of the arts. - Bring in Sabrina Kline from ACOE |  |
|  | Develop a PR brochure/poster for AUSD |  |
|  | Initiate advocacy programs for – administrators – teachers – community |  |
|  | Access District Website to communicate arts programs and events |  |
|  | Budget: Approximately $10,000 – Ongoing Art & Music Block Grant |  |
| III. Focus Area: Resources – Ongoing Art & Music Block Grant - $165,748 |  |  |
| GOAL #5: Support and develop VAPA programming through community/school partnerships |  |  |
|  | Phase I (2007-2009) Suggested Strategies, actions, and activities: | Phase II (2009-2012) Suggested Strategies, actions, and activities |
|  | Initiate expanded connection with Parks and Recreation | Develop a City-wide resource guide for teachers |
|  | Collaborate and share resources with other districts | Develop an AUSD District Orchestra (i.e., Alameda Youth Orchestra for interested students) |
|  | Secure sponsors and patrons for the arts |  |
|  | Provide initiation/coordination of “Artist Adopt a School” programs |  |
|  | Initiate a P.S.S. – Parent, Staff and Student site committees at each school that would extend and showcase the arts beyond the walls of the school |  |
|  | Survey community for community artists who will work with schools |  |
|  | Liaison with the Frank Bett’s Center of the Arts & Rhythmix Cultural Center |  |
|  | Tap into the Alameda Multicultural Center to provide art instruction |  |
|  | Budget: Approximately $5,000 – Ongoing Art & Music Block Grant |  |
| III. Focus Area: Resources – Ongoing Art & Music Block Grant - $165,748 |  |  |
| GOAL #6 - Ensure that all schools have adequate supplies/equipment and dedicated, exemplary facilities designed to support VAPA programs |  |  |
|  | Phase I (2007-2009) Suggested Strategies, actions, and activities: | Phase II (2009-2012) Suggested Strategies, actions, and activities |
|  | Provide for adequate supplies and equipment for the arts, theatre, music (i.e. instruments), and dance on a continuing basis | Advocate for a Performing Arts facility at Encinal High School |
|  | Get needs assessment of all VAPA teaching facilities | Ensure that every music teacher has a dedicated classroom and space for their equipment |
|  | Budget: Approximately $50,000 – Site One-Time Art & Music funding | Establish a performing arts center for the use of all disciplines |
|  |  | Renovate and develop joint use of current citywide buildings for VAPA facility use. - Alameda Public Library’s Media Center (Photoshop, Illustrator, or other graphic design sorftware, etc.) - Kofman Theater – dance, music, etc. |
| III. Focus Area: Resources – Ongoing Art & Music Block Grant - $165,748 |  |  |
| GOAL #7 - Fund a sustainable and equitable VAPA budget within AUSD. |  |  |
|  | Phase I (2007-2009) Suggested Strategies, actions, and activities: | Phase II (2009-2012) Suggested Strategies, actions, and activities |
|  | Submit arts plan and budget for board approval - Prioritize ongoing art and music block grant funding. | Ensure on-going funding for VAPA programming |
|  | Expand AEF’s involvement to support funding for the variety of arts education as they do for music. | Research grants and corporate-giving opportunities. |
|  | Hire/Contract a person to procure funding for arts via – partnerships, grants, etc. and build community advocacy |  |
|  | Coordinate all collective funding sources for the arts to achieve VAPA goals. |  |
|  | Explore leasing by district facilities to directly go towards maintenance of these facilities. |  |
|  | Hire a skilled lobbyist (For VAPA) - Join the CAAE as an institutional member (this group will lobby for the arts) |  |
|  | Budget: Approximately $5,000 – Ongoing Art & Music Block Grant; there may be revenue enhancement |  |
| IV. Focus Area: Policy |  |  |
| GOAL 8: Ensure qualified leadership that advocates for the needs of VAPA program |  |  |
|  | Phase I (2007-2009) Suggested Strategies, actions, and activities: | Phase II (2009-2012) Suggested Strategies, actions, and activities |
|  | Provide ongoing VAPA Committee meetings to implement, monitor, and evaluate the 5-year Arts Education Plan, which includes an annual report to the Board: - 4 meetings/year (1 meeting per quarter) - 2 meetings during the school day, 2 after school (teachers either would receive substitutes or hourly) - Establish VAPA subcommittees-one committee per focus area - Select co-chairs for each focus area subcommittee | Maintain a VAPA committee to oversee and help implement VAPA plan |
|  | Assign VAPA committee member(s) to represent AUSD at ACOE MAP network | Hire a district arts coordinator for networking/PR, scheduling meeting institutional connections, facilitates staff development. (budget amount: $25,000) |
|  | Create a Board Approved Vision Statement re: VAPA - Resolution must include language that speaks to inclusive arts education as essential to well-rounded education |  |
|  | Assign representative to serve on the District Curriculum Committee |  |
|  | Budget: Approximately $25,000 – Ongoing Art & Music Block Grant |  |